## Pot 3
Change Type | Count
New Entries | 1
Deleted Entries | 0
Modified Entries | 1
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
NEW | New entry in TEC register. | North Kyle New Cumnock | NORTH KYLE WIND FARM LIMITED | North Kyle 132/33kV substation | 2.0 | 79.0 | 133.0 | 212.0 | 2026-02-04 | Built | Direct Connection | SPT | Wind Offshore | a0l4L0000005inuQAA | PRO-000474-2 | 2
MODIFIED | Connection Date: '2026-08-01' -> '2029-12-31' | Rampion Extension Offshore Wind Farm | RAMPION EXTENSION DEVELOPMENT LIMITED | Bolney 400kV Substation |  | 0.0 | 1200.0 | 1200.0 | 2029-12-31 | Scoping | Direct Connection | NGET | Wind Offshore | a0l4L0000005io1QAA | PRO-000467

## Pot 1
Change Type | Count
New Entries | 1
Deleted Entries | 1
Modified Entries | 3
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
NEW | New entry in TEC register. | North Kyle New Cumnock | NORTH KYLE WIND FARM LIMITED | North Kyle 132/33kV substation | 1.0 | 79.0 |  | 79.0 | 2025-02-28 | Built | Direct Connection | SPT | Wind Onshore | a0l4L0000005inuQAA | PRO-000474-1 | 2
DELETED | Entry removed from TEC register. | North Kyle New Cumnock | NORTH KYLE WIND FARM LIMITED | North Kyle 132/33kV substation |  | 212.0 | 0.0 | 212.0 |  | Built | Direct Connection | SPT | Wind Onshore | a0l4L0000005inuQAA | PRO-000474
MODIFIED | Connection Date: '2027-04-01' -> '2029-08-31' | Glen Ullinish Extension | GLEN ULLINISH WF 2 LTD | Glen Ullinish Extension 132/33kV Substation |  | 0.0 | 240.0 | 240.0 | 2029-08-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0l4L0000005iYiQAI | PRO-001346
MODIFIED | Connection Date: '2026-10-31' -> '2028-04-16' | Glen Ullinish Wind Farm | GLEN ULLINISH WF LIMITED | Glen Ullinish 132/33kV Substation |  | 0.0 | 49.9 | 49.9 | 2028-04-16 | Consents Approved | Direct Connection | SHET | Wind Onshore | a0l4L0000005isHQAQ | PRO-000298
MODIFIED | Connection Date: '2027-04-07' -> '2028-04-07' | Lorg Wind Farm | RWE Renewables UK Onshore Wind Limited | Lorg Wind Farm 132/32kV |  | 0.0 | 69.5 | 69.5 | 2028-04-07 | Scoping | Direct Connection | SPT | Wind Onshore | a0l4L0000005ikXQAQ | PRO-000153