## Pot 3
Change Type | Count
New Entries | 0
Deleted Entries | 0
Modified Entries | 0
Detailed Change Records:

## Pot 1
Change Type | Count
New Entries | 1
Deleted Entries | 2
Modified Entries | 4
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
NEW | New entry in TEC register. | Strathy Wood Wind Farm | RWE Renewables UK Onshore Wind Limited | Strathy Wood 132/33kV Substation |  | 0.0 | 63.5 | 63.5 | 2029-12-31 | Consents Approved | Direct Connection | SHET | Wind Onshore | a0l4L0000005ionQAA | PRO-000154 | 2
DELETED | Entry removed from TEC register. | Strathy Wood Wind Farm | RWE Renewables UK Onshore Wind Limited | Strathy Wood 132/33kV Substation | 1.0 | 0.0 | 54.4 | 54.4 | 2026-09-30 | Consents Approved | Direct Connection | SHET | Wind Onshore | a0l4L0000005ionQAA | PRO-000154-1
DELETED | Entry removed from TEC register. | Strathy Wood Wind Farm | RWE Renewables UK Onshore Wind Limited | Strathy Wood 132/33kV Substation | 2.0 | 0.0 | 9.1 | 63.5 | 2026-09-30 | Consents Approved | Direct Connection | SHET | Wind Onshore | a0l4L0000005ionQAA | PRO-000154-2
MODIFIED | Connection Date: '2028-10-30' -> '2029-10-30' | Cilfynydd Green Energy Centre | CILFYNYDD NG LIMITED | Cilfynydd 400kV Substation | 1 | 0.0 | 400.0 | 400.0 | 2029-10-30 | Awaiting Consents | Direct Connection | NGET | Demand;Energy Storage System;PV Array (Photo Voltaic/solar);Wind Onshore | a0l4L0000005idMQAQ | PRO-001663-1 | 1
MODIFIED | Connection Date: '2026-10-31' -> '2029-07-30' | Fleet (Tertiary) | CSE23 LIMITED | Fleet 400kV Substation |  | 0.0 | 47.5 | 47.5 | 2029-07-30 | Consents Approved | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | a0l4L0000005izAQAQ | PRO-001087
MODIFIED | Gate Status: '' -> '1' | Halbeath | HALBEATH SOLAR LTD | Halbeath 132kV Substation |  | 0.0 | 150.0 | 150.0 | 2029-07-31 | Scoping | Direct Connection | SPT | Demand;Energy Storage System;PV Array (Photo Voltaic/solar);Reactive Compensation | a0l4L0000005ivDQAQ | PRO-002266 | 1
MODIFIED | Gate Status: '' -> '2' | Iron Acton | IRON ACTON GREEN LIMITED | 132kV bay at Iron Acton Substation | 2 | 0.0 | 20.6 | 120.0 | 2026-09-30 | Consents Approved | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005iodQAA | PRO-000491-2 | 2