## Pot 3
Change Type | Count
New Entries | 0
Deleted Entries | 0
Modified Entries | 0
Detailed Change Records:

## Pot 1
Change Type | Count
New Entries | 0
Deleted Entries | 3
Modified Entries | 7
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
DELETED | Entry removed from TEC register. | Elmya Gissing BESS & PV | RPC ELMYA CARNATION GISSING LIMITED | North Anglia Connection Node A 400kV |  | 0.0 | 900.0 | 900.0 | 2034-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012jJxAAI | PRO-004657 | 1
DELETED | Entry removed from TEC register. | Elmya Kilworth BESS & PV | RPC ELMYA CARNATION KILWORTH LIMITED | Derbyshire Connection Node H 400kV Substation |  | 0.0 | 850.0 | 850.0 | 2037-10-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012khrAAA | PRO-004739 | 1
DELETED | Entry removed from TEC register. | Elmya Morningside BESS & PV | ELMYA RPC UK MORNINGSIDE LIMITED | Elmya Morningside 400kV Substation |  | 0.0 | 400.0 | 400.0 | 2033-10-31 | Scoping | Direct Connection | SPT | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012fGMAAY | PRO-004396 | 1
MODIFIED | Gate Status: '' -> '1' | Astwood Solar Farm GEC | ASTWOOD GREEN ENERGY LTD | West Anglia Connection Node G 400kV Substation |  | 0.0 | 520.0 | 520.0 | 2034-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0lJ9000000blKHIAY | PRO-004799 | 1
MODIFIED | Gate Status: '' -> '2' | Bilbo Farm | LEL BILBO SOLAR LIMITED | Strichen 132/33kV GSP Substation | 1 | 0.0 | 25.0 | 25.0 | 2024-10-31 | Scoping | Embedded | SHET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005iXhQAI | PRO-001301-1 | 2
MODIFIED | Gate Status: '' -> '1' | Enoch Hill 2 Wind Farm | RWE Renewables UK Onshore Wind Limited | Enoch Hill 2 Wind Farm 33kV Substation |  | 0.0 | 10.0 | 10.0 | 2027-04-30 | Awaiting Consents | Direct Connection | SPT | Energy Storage System;Wind Onshore | a0l4L0000005indQAA | PRO-000478 | 1
MODIFIED | Gate Status: '' -> '1' | Market Harborough GEC (Ethos Green) | MARKET HARBOROUGH GREEN ENERGY CENTRE LTD | Market Harborough 400kV Substation |  | 0.0 | 560.0 | 560.0 | 2032-10-31 | Awaiting Consents | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000ViF4AAK | PRO-004343 | 1
MODIFIED | Connection Date: '2025-07-01' -> '2026-04-24' | Pencloe Windfarm | PENCLOE WIND ENERGY LIMITED | Pencloe 132/33kV Substation | 1 | 0.0 | 85.0 | 85.0 | 2026-04-24 | Consents Approved | Direct Connection | SPT | Energy Storage System;Wind Onshore | a0l4L0000005isjQAA | PRO-000323-1
MODIFIED | Connection Date: '2026-10-09' -> '2026-12-18' | Stranoch Wind Farm | Stranoch Windfarm Limited | Stranoch Wind 132/33kV Substation |  | 0.0 | 102.0 | 102.0 | 2026-12-18 | Consents Approved | Direct Connection | SPT | Wind Onshore | a0l4L0000005inqQAA | PRO-000127
MODIFIED | Connection Date: '2027-04-25' -> '2027-05-28' | Strathy South Wind | SSE Generation Limited | Strathy South 132/33kV Substation |  | 0.0 | 207.6 | 207.6 | 2027-05-28 | Scoping | Direct Connection | SHET | Wind Onshore | a0l4L0000005ix6QAA | PRO-000183