## Pot 3
Change Type | Count
New Entries | 0
Deleted Entries | 1
Modified Entries | 1
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
DELETED | Entry removed from TEC register. | Celtic 2 Offshore Wind Farm | RWE Offshore Wind | Alverdiscott 400kV Substation |  | 0.0 | 1000.0 | 1000.0 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | a0l4L0000005ia5QAA | PRO-002007 | 1
MODIFIED | Connection Date: '2027-10-31' -> '2028-04-03'; Gate Status: '' -> '2' | Pentland Floating Offshore Wind Farm | HIGHLAND WIND LIMITED | Pentland Floating Offshore Wind Farm 132/66kV substation |  | 0.0 | 100.0 | 100.0 | 2028-04-03 | Consents Approved | Direct Connection | SHET | Wind Offshore | a0l4L0000005idGQAQ | PRO-001472 | 2

## Pot 1
Change Type | Count
New Entries | 0
Deleted Entries | 1
Modified Entries | 12
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
DELETED | Entry removed from TEC register. | Willington Green Energy Centre | WILLINGTON NG LIMITED | Willington 400kV Substation | 3.0 | 0.0 | 0.0 | 0.0 | 2037-10-30 | Scoping | Direct Connection | NGET | Demand;Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005ikHQAQ | PRO-001797-3
MODIFIED | Gate Status: '' -> '1' | Berwick Solar Wind and Battery Storage | BERWICK RENEWABLES TX LIMITED | Berwick 132/33kV |  | 0.0 | 100.0 | 100.0 | 2031-10-31 | Scoping | Direct Connection | SPT | Energy Storage System;PV Array (Photo Voltaic/solar);Wind Onshore | a0l8e0000011xxoAAA | PRO-003490 | 1
MODIFIED | Gate Status: '' -> '1' | BlaenCothi Energy Park | BLAENCOTHI ENERGY PARK LIMITED | Pont Abraham GSP |  | 0.0 | 145.0 | 145.0 | 2028-10-31 | Scoping | Embedded | NGET | Wind Onshore | a0l4L0000005iRaQAI | PRO-001920 | 1
MODIFIED | Gate Status: '' -> '1' | Braintree | Braintree 10 Renewables Limited | Braintree 400kV Substation |  | 0.0 | 1000.0 | 1000.0 | 2034-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000TPQgAAO | PRO-003406 | 1
MODIFIED | Gate Status: '' -> '1' | Feckenham | ENSO GREEN HOLDINGS X LIMITED | Feckenham 400kV Substation |  | 0.0 | 400.0 | 400.0 | 2036-10-31 | Awaiting Consents | Direct Connection | NGET | Demand;Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005ikrQAA | PRO-002189 | 1
MODIFIED | Gate Status: '' -> '2' | Indian Queens Energy Centre | IQ ENERGY CENTRE LIMITED | Indian Queens 400kV Substation |  | 0.0 | 47.5 | 47.5 | 2027-05-30 | Consents Approved | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005iZCQAY | PRO-001371 | 2
MODIFIED | Connection Date: '2026-06-30' -> '2026-12-31'; Gate Status: '' -> '2' | Keithick 16 Solar & BESS | SIRIUS ECODEV (KEITHICK) LTD | Coupar Angus 132/33kV GSP |  | 0.0 | 16.0 | 16.0 | 2026-12-31 | Consents Approved | Embedded | SHET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005iQXQAY | PRO-001890 | 2
MODIFIED | Gate Status: '' -> '1' | Loch Luichart Extension II | BLUEBELL WIND FARM LIMITED | Loch Luichart Extension II Substation |  | 0.0 | 36.0 | 36.0 | 2024-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0l4L0000005inUQAQ | PRO-000487 | 1
MODIFIED | Gate Status: '' -> '1' | Maesnant Energy Park | Maesnant Energy Park Limited | Chirk GSP |  | 0.0 | 150.0 | 150.0 | 2033-11-01 | Scoping | Embedded | NGET | Wind Onshore | a0l4L0000005iRZQAY | PRO-001919 | 1
MODIFIED | Gate Status: '' -> '1' | Wakeleys BESS | EPL NEWCO6 LIMITED | Wakeleys 400kV |  | 0.0 | 480.0 | 480.0 | 2033-10-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000f5BxAAI | PRO-003921 | 1
MODIFIED | Capacity: '1025.0' -> '400.0' | Willington Green Energy Centre | WILLINGTON NG LIMITED | Willington 400kV Substation | 1 | 0.0 | 400.0 | 400.0 | 2028-10-30 | Scoping | Direct Connection | NGET | Demand;Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005ikHQAQ | PRO-001797-1
MODIFIED | Connection Date: '2025-10-31' -> '2027-05-30' | Wymondley | Priory Generation Limited | Wymondley 400kV Substation |  | 0.0 | 57.0 | 57.0 | 2027-05-30 | Awaiting Consents | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005iOgQAI | PRO-001245
MODIFIED | Connection Date: '2025-10-31' -> '2027-05-30' | Wymondley Solar Farm | AGR SOLAR 4 LIMITED | Wymondley 400/33kV Substation |  | 0.0 | 50.0 | 50.0 | 2027-05-30 | Consents Approved | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005igqQAA | PRO-001105