## Pot 3 (Offshore Wind)
TEC Register Comparison: Pot 3 (Offshore Wind)
Version A: tec-register-2024-12-06.csv | Version B: tec-register-2025-12-18.csv
SUMMARY OF PROJECT CHANGES:
Metric | Value
Projects Added (in B only) | 2
Projects Removed (in A only) | 0
Projects with Field Change (excluding Added/Removed) | 58
--- | ---
Capacity Added (MW) | 1,450.00
Capacity Removed (MW) | 0.00
--- DETAILED PROJECT CHANGES ---
'ADDED' and 'CHANGED' rows show Version B (Latest) data.
'REMOVED' rows show Version A (Old) data.
Project ID | Project Name | Changes Made | Change_Type | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project Number | Gate
a0l8e0000012hnbAAA | INTOG 2 | NEWLY ADDED PROJECT | ADDED | CERULEAN WINDS LIMITED | Thorntonloch 400kV Substation |  | 0 | 1400 | 1400 | 2032-06-30 | Scoping | Direct Connection | SPT | Wind Offshore | PRO-004514
a0l8e0000012kiGAAQ | Project Flora Peterhead | NEWLY ADDED PROJECT | ADDED | BP NORTH EAST OFFSHORE WIND LIMITED | Peterhead Grange GSP |  | 0 | 50 | 50 | 2033-10-31 | Scoping | Embedded | SHET | Wind Offshore | PRO-004741
a0l4L0000005iipQAA | Celtic Sea Offshore Wind Farm | REMOVED PROJECT | REMOVED | CELTIC SEA OFFSHORE WIND FARM LIMITED | Alverdiscott 400kV Substation | 1 | 0 | 400 | 400 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001763-1
a0l4L0000005iipQAA | Celtic Sea Offshore Wind Farm | REMOVED PROJECT | REMOVED | CELTIC SEA OFFSHORE WIND FARM LIMITED | Alverdiscott 400kV Substation | 2 | 0 | 1000 | 1400 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001763-2
a0l4L0000005ihFQAQ | EOLFI Offshore | REMOVED PROJECT | REMOVED | Shell New Energies UK Ltd | Eolfi Offshore Substation |  | 0 | 3000 | 3000 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001538
a0l8e000000TPOFAA4 | ARVEN OFFSHORE WIND FARM | Connection Site: Arven 400/66kV Offshore Substation -> Blackhillock 400kV Substation | CHANGED | ARVEN OFFSHORE WIND FARM LIMITED | Blackhillock 400kV Substation |  | 0 | 1800 | 1800 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-003288
a0l8e000001HxQ5AAK | Arven South Offshore Wind Farm | Connection Site: Arven South 275kV Offshore Substation -> Kergord GSP | CHANGED | ARVEN SOUTH LIMITED | Kergord GSP |  | 0 | 500 | 500 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-004242
a0l4L0000005ipBQAQ | Awel Y Mor | Project Name: Awel Y Mor Extension -> Awel Y Mor | CHANGED | AWEL Y MOR OFFSHORE WIND FARM LIMITED | Bodelwyddan 400kV Substation | 1 | 0 | 574 | 574 | 2027-04-01 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000529-1
a0l4L0000005ipBQAQ | Awel Y Mor | Project Name: Awel Y Mor Extension -> Awel Y Mor | CHANGED | AWEL Y MOR OFFSHORE WIND FARM LIMITED | Bodelwyddan 400kV Substation | 2 | 0 | 526 | 1100 | 2028-04-01 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000529-2
a0l4L0000005izEQAQ | Bellrock Offshore Wind Farm | Customer Name: BLUEFLOAT ENERGY UK HOLDINGS LIMITED -> Bellrock Offshore Wind Farm Limited; Connection Site: Lyra 320/66kV Offshore Substation -> Hurlie 400kV substation; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 1,200.00 MW -> 3,000.00 MW; MW Effective From: 31/10/2033 -> 31/10/2032; HOST TO: SPT -> SHET; Project Number: PRO-001496 -> PRO-001496-1 | CHANGED | Bellrock Offshore Wind Farm Limited | Hurlie 400kV substation | 1 | 0 | 1200 | 1200 | 2032-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001496-1
a0l4L0000005izEQAQ | Bellrock Offshore Wind Farm | Customer Name: BLUEFLOAT ENERGY UK HOLDINGS LIMITED -> Bellrock Offshore Wind Farm Limited; Connection Site: Lyra 320/66kV Offshore Substation -> Hurlie 400kV substation; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 1,200.00 MW -> 3,000.00 MW; MW Effective From: 31/10/2033 -> 31/10/2032; HOST TO: SPT -> SHET; Project Number: PRO-001496 -> PRO-001496-1 | CHANGED | Bellrock Offshore Wind Farm Limited | Hurlie 400kV substation | 2 | 0 | 600 | 1800 | 2035-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001496-2
a0l8e0000010wTnAAI | Berwick Bank Offshore Wind Farm A | Connection Site: Berwick Bank A 275/66kV Offshore Substation -> Branxton 400/132KV Substation; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 1,150.00 MW -> 2,530.00 MW; Project Number: PRO-002627 -> PRO-002627-1 | CHANGED | BERWICK BANK A LIMITED | Branxton 400/132KV Substation | 1 | 0 | 1150 | 1150 | 2028-10-31 | Scoping | Direct Connection | SPT | Wind Offshore | PRO-002627-1
a0l8e0000010wTnAAI | Berwick Bank Offshore Wind Farm A | Connection Site: Berwick Bank A 275/66kV Offshore Substation -> Branxton 400/132KV Substation; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 1,150.00 MW -> 2,530.00 MW; Project Number: PRO-002627 -> PRO-002627-1 | CHANGED | BERWICK BANK A LIMITED | Branxton 400/132KV Substation | 2 | 0 | 230 | 1380 | 2029-10-31 | Scoping | Direct Connection | SPT | Wind Offshore | PRO-002627-2
a0l8e000000snsQAAQ | Berwick Bank Offshore Wind Farm B | Connection Site: Berwick Bank B 275/66kV Offshore Substation -> Branxton 400/132KV Substation; MW Increase / Decrease: 250.0 -> 1150.0; Cumulative Total Capacity (MW): 1,400.00 MW -> 2,530.00 MW; MW Effective From: 30/10/2029 -> 31/10/2029 | CHANGED | Berwick Bank B Limited | Branxton 400/132KV Substation | 1 | 0 | 1150 | 1150 | 2029-10-31 | Scoping | Direct Connection | SPT | Wind Offshore | PRO-002628-1
a0l8e000000snsQAAQ | Berwick Bank Offshore Wind Farm B | Connection Site: Berwick Bank B 275/66kV Offshore Substation -> Branxton 400/132KV Substation; MW Increase / Decrease: 250.0 -> 1150.0; Cumulative Total Capacity (MW): 1,400.00 MW -> 2,530.00 MW; MW Effective From: 30/10/2029 -> 31/10/2029 | CHANGED | Berwick Bank B Limited | Branxton 400/132KV Substation | 2 | 0 | 230 | 1380 | 2031-06-30 | Scoping | Direct Connection | SPT | Wind Offshore | PRO-002628-2
a0l4L0000005idoQAA | Bowdun (ex Cluaran Deas Ear) Offshore Wind Farm | Connection Site: New Deer 2 400kV Substation -> Hurlie 400kV substation; MW Effective From: 31/10/2033 -> 31/12/2035 | CHANGED | BOWDUN OFFSHORE WIND FARM LIMITED | Hurlie 400kV substation |  | 0 | 1008 | 1008 | 2035-12-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-002091
a0l4L0000005itdQAA | Broadshore Offshore Wind Farm | Customer Name: BLUEFLOAT ENERGY UK HOLDINGS LIMITED -> Broadshore Offshore Wind Farm Limited; Connection Site: New Deer 2 400kV Substation -> Longside 400kV Substation | CHANGED | Broadshore Offshore Wind Farm Limited | Longside 400kV Substation |  | 0 | 900 | 900 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-002171
a0l4L0000005izLQAQ | Buchan 01 Offshore Wind Farm | MW Increase / Decrease: 932.0 -> 960.0; Cumulative Total Capacity (MW): 932.00 MW -> 960.00 MW | CHANGED | BUCHAN OFFSHORE WIND LIMITED | Buchan 01 275/66kV Substation |  | 0 | 960 | 960 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001528
a0l4L0000005ia5QAA | Celtic 2 Offshore Wind Farm | Customer Name: RWE RENEWABLES UK LIMITED -> RWE Renewables UK Limited | CHANGED | RWE Renewables UK Limited | Alverdiscott 400kV Substation |  | 0 | 1000 | 1000 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-002007
a0l4L0000005ihkQAA | Celtic Offshore Wind Farm | Customer Name: RWE RENEWABLES UK LIMITED -> RWE Renewables UK Limited | CHANGED | RWE Renewables UK Limited | Alverdiscott 400kV Substation |  | 0 | 400 | 400 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001760
a0l4L0000005idWQAQ | Dogger Bank D Offshore Wind Farm | Project Name: Gatroben Offshore Wind Farm -> Dogger Bank D Offshore Wind Farm; Customer Name: GATROBEN OFFSHORE DEVELOPMENTS 2 LIMITED -> Doggerbank Offshore Wind Farm Project 4 Projco Limited; Connection Site: Gatroben Offshore Substation -> Birkhill Wood 400kV Substation; MW Increase / Decrease: 1320.0 -> 1450.0; Cumulative Total Capacity (MW): 1,320.00 MW -> 1,450.00 MW | CHANGED | Doggerbank Offshore Wind Farm Project 4 Projco Limited | Birkhill Wood 400kV Substation |  | 0 | 1450 | 1450 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001675
a0l4L0000005imQQAQ | Dogger Bank Project 4 (Dogger Bank B) | MW Connected: 0.0 -> 1200.0; MW Increase / Decrease: 1200.0 -> 0.0; MW Effective From: 01/04/2024 -> NULL; Project Status: Under Construction/Commissioning -> Built | CHANGED | DOGGERBANK OFFSHORE WIND FARM PROJECT 2 PROJCO LIMITED | Dogger Bank 220kV Offshores |  | 1200 | 0 | 1200 |  | Built | Direct Connection | NGET | Wind Offshore | PRO-000410
a0l4L0000005imRQAQ | Dogger Bank Project C | Connection Site: Lackenby GSP -> Teeside Connection Node A 132kV Substation | CHANGED | DOGGERBANK OFFSHORE WIND FARM PROJECT 3 PROJCO LIMITED | Teeside Connection Node A 132kV Substation |  | 0 | 1200 | 1200 | 2025-04-01 | Consents Approved | Direct Connection | NGET | Wind Offshore | PRO-000409
a0l4L0000005iZFQAY | Dogger Bank South East | Project Name: North Sea -> Dogger Bank South East; Customer Name: RWE RENEWABLES UK LIMITED -> RWE Renewables UK Dogger Bank South (East) Limited; Connection Site: RWE North Sea Offshore Substation -> Birkhill Wood 400kV Substation; Stage: NULL -> 1.0; MW Increase / Decrease: 1500.0 -> 400.0; Cumulative Total Capacity (MW): 1,500.00 MW -> 1,850.00 MW; MW Effective From: 01/01/2033 -> 30/10/2030; Project Number: PRO-001375 -> PRO-001375-1 | CHANGED | RWE Renewables UK Dogger Bank South (East) Limited | Birkhill Wood 400kV Substation | 1 | 0 | 400 | 400 | 2030-10-30 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001375-1
a0l4L0000005iZFQAY | Dogger Bank South East | Project Name: North Sea -> Dogger Bank South East; Customer Name: RWE RENEWABLES UK LIMITED -> RWE Renewables UK Dogger Bank South (East) Limited; Connection Site: RWE North Sea Offshore Substation -> Birkhill Wood 400kV Substation; Stage: NULL -> 1.0; MW Increase / Decrease: 1500.0 -> 400.0; Cumulative Total Capacity (MW): 1,500.00 MW -> 1,850.00 MW; MW Effective From: 01/01/2033 -> 30/10/2030; Project Number: PRO-001375 -> PRO-001375-1 | CHANGED | RWE Renewables UK Dogger Bank South (East) Limited | Birkhill Wood 400kV Substation | 2 | 0 | 1050 | 1450 | 2031-11-30 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001375-2
a0l4L0000005iZnQAI | Dogger Bank South West | Project Name: Dogger Bank South West (was Irish Sea) -> Dogger Bank South West; Customer Name: RWE RENEWABLES UK LIMITED -> RWE RENEWABLES UK DOGGER BANK SOUTH (WEST) LIMITED; Connection Site: Wylfa 400kV Substation -> Birkhill Wood 400kV Substation; Stage: NULL -> 1.0; MW Increase / Decrease: 1500.0 -> 400.0; Cumulative Total Capacity (MW): 1,500.00 MW -> 1,850.00 MW; MW Effective From: 01/04/2033 -> 30/10/2030; Project Number: PRO-001386 -> PRO-001386-1 | CHANGED | RWE RENEWABLES UK DOGGER BANK SOUTH (WEST) LIMITED | Birkhill Wood 400kV Substation | 1 | 0 | 400 | 400 | 2030-10-30 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001386-1
a0l4L0000005iZnQAI | Dogger Bank South West | Project Name: Dogger Bank South West (was Irish Sea) -> Dogger Bank South West; Customer Name: RWE RENEWABLES UK LIMITED -> RWE RENEWABLES UK DOGGER BANK SOUTH (WEST) LIMITED; Connection Site: Wylfa 400kV Substation -> Birkhill Wood 400kV Substation; Stage: NULL -> 1.0; MW Increase / Decrease: 1500.0 -> 400.0; Cumulative Total Capacity (MW): 1,500.00 MW -> 1,850.00 MW; MW Effective From: 01/04/2033 -> 30/10/2030; Project Number: PRO-001386 -> PRO-001386-1 | CHANGED | RWE RENEWABLES UK DOGGER BANK SOUTH (WEST) LIMITED | Birkhill Wood 400kV Substation | 2 | 0 | 1050 | 1450 | 2031-11-30 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001386-2
a0l4L0000005irNQAQ | East Anglia One North | Connection Site: EA1N 275/66kV Offshore Platform -> Friston 400kV Substation; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 860.00 MW -> 1,740.00 MW; MW Effective From: 31/03/2028 -> 30/10/2029; Project Number: PRO-000269 -> PRO-000269-1 | CHANGED | EAST ANGLIA ONE LIMITED | Friston 400kV Substation | 1 | 0 | 860 | 860 | 2029-10-30 | Awaiting Consents | Direct Connection | NGET | Wind Offshore | PRO-000269-1
a0l4L0000005irNQAQ | East Anglia One North | Connection Site: EA1N 275/66kV Offshore Platform -> Friston 400kV Substation; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 860.00 MW -> 1,740.00 MW; MW Effective From: 31/03/2028 -> 30/10/2029; Project Number: PRO-000269 -> PRO-000269-1 | CHANGED | EAST ANGLIA ONE LIMITED | Friston 400kV Substation | 2 | 0 | 20 | 880 | 2034-10-31 | Awaiting Consents | Direct Connection | NGET | Wind Offshore | PRO-000269-2
a0l4L0000005inxQAA | Erebus | Customer Name: BLUE GEM WIND LIMITED -> Blue Gem Wind Limited | CHANGED | Blue Gem Wind Limited | Pembroke 132kV Substation |  | 0 | 95.25 | 95.25 | 2028-07-26 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000471
a0l8e000000f8QCAAY | Equinor Celtic Sea 1 | Plant Type: Energy Storage System;Wind Offshore -> Wind Offshore | CHANGED | EQUINOR NEW ENERGY LIMITED | Alverdiscott 400kV Substation |  | 0 | 1000 | 1000 | 2036-12-06 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-004037
a0l8e000000f8QHAAY | Equinor Celtic Sea 2 | Plant Type: Energy Storage System;Wind Offshore -> Wind Offshore | CHANGED | EQUINOR NEW ENERGY LIMITED | Alverdiscott 400kV Substation |  | 0 | 1000 | 1000 | 2036-12-06 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-004038
a0l4L0000005iqiQAA | Gunfleet Sands II Offshore Wind Farm | HOST TO: OFTO -> NGET | CHANGED | Gunfleet Sands II Ltd | Gunfleet Sands 33/132kV Offshore |  | 64 | 0 | 64 |  | Built | Direct Connection | NGET | Wind Offshore | PRO-000229
a0l4L0000005iqJQAQ | Gunfleet Sands Offshore Wind Farm | HOST TO: OFTO -> NGET | CHANGED | GUNFLEET SANDS LIMITED | Gunfleet Sands 33/132kV Offshore |  | 99.9 | 0 | 99.9 |  | Built | Direct Connection | NGET | Wind Offshore | PRO-000224
a0l4L0000005iNUQAY | Havbredey | Customer Name: Northland Power UK Limited -> HAVBREDEY LIMITED; Connection Site: NPI A 275/66kV Offshore Substation -> New Dounreay 400kV substation | CHANGED | HAVBREDEY LIMITED | New Dounreay 400kV substation |  | 0 | 1500 | 1500 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001628
a0l4L0000005it3QAA | Inch Cape Offshore Wind Farm Platform 1 | MW Effective From: 21/06/2026 -> 21/02/2026 | CHANGED | INCH CAPE OFFSHORE LIMITED | Cockenzie 400/275kV |  | 0 | 540 | 540 | 2026-02-21 | Consents Approved | Direct Connection | SPT | Wind Offshore | PRO-000348
a0l4L0000005it4QAA | Inch Cape Offshore Wind Farm Platform 2 | MW Effective From: 21/06/2026 -> 21/02/2026 | CHANGED | INCH CAPE OFFSHORE LIMITED | Cockenzie 400/275kV |  | 0 | 540 | 540 | 2026-02-21 | Consents Approved | Direct Connection | SPT | Wind Offshore | PRO-000349
a0l4L0000005iZNQAY | Llŷr Floating Wind | MW Increase / Decrease: 1800.0 -> 200.0; Cumulative Total Capacity (MW): 1,800.00 MW -> 200.00 MW; MW Effective From: 31/10/2031 -> 31/10/2028 | CHANGED | Llŷr Floating Wind Limited | Pembroke 400kV Substation |  | 0 | 200 | 200 | 2028-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001981
a0l4L0000005iySQAQ | Llywelyn Extension Offshore Wind Farm | Customer Name: RENANTIS UK LIMITED -> Renantis UK Limited | CHANGED | Renantis UK Limited | Pembroke 400kV Substation |  | 0 | 1000 | 1000 | 2036-12-06 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-002406
a0l4L0000005idPQAQ | Llywelyn Floating Offshore Wind Farm | Customer Name: RENANTIS UK LIMITED -> Renantis UK Limited | CHANGED | Renantis UK Limited | Pembroke 400kV Substation |  | 0 | 300 | 300 | 2029-03-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001668
a0l4L0000005iisQAA | Magwind | Customer Name: MAGNORA OFFSHORE WIND AS -> MAGNORA OFFSHORE WIND N3 LIMITED; Connection Site: New Dounreay -> Talisk Offshore Wind Farm | CHANGED | MAGNORA OFFSHORE WIND N3 LIMITED | Talisk Offshore Wind Farm |  | 0 | 495 | 495 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001766
a0l4L0000005iZbQAI | Merlin 2 Offshore Windfarm | Gate: -> 1.0 | CHANGED | OFFSHORE WIND LIMITED | Alverdiscott 400kV Substation |  | 0 | 1500 | 1500 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001997 | 1
a0l4L0000005ihVQAQ | Merlin Offshore Wind Farm | Gate: -> 1.0 | CHANGED | OFFSHORE WIND LIMITED | Alverdiscott 400kV Substation |  | 0 | 300 | 300 | 2028-11-01 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001728 | 1
a0l4L0000005ifSQAQ | Moray West Offshore Windfarm | Stage: 1.0 -> NULL; MW Connected: 0.0 -> 860.0; MW Increase / Decrease: 800.0 -> 0.0; Cumulative Total Capacity (MW): 1,660.00 MW -> 860.00 MW; MW Effective From: 01/04/2024 -> NULL; Project Status: Consents Approved -> Built; Project Number: PRO-001130-1 -> PRO-001130 | CHANGED | MORAY OFFSHORE WINDFARM (WEST) LIMITED | Moray Firth 220/33kV Platform 1 & 2 Offshore Substation |  | 860 | 0 | 860 |  | Built | Direct Connection | SHET | Wind Offshore | PRO-001130
a0l4L0000005ibwQAA | Morecambe Offshore Wind Farm | Customer Name: OFFSHORE WIND LIMITED -> MORECAMBE OFFSHORE WINDFARM LTD | CHANGED | MORECAMBE OFFSHORE WINDFARM LTD | Penwortham 400kV Substation |  | 0 | 480 | 480 | 2029-06-30 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001450
a0l4L0000005izJQAQ | Morven A Offshore Wind Farm (Prev Phoenix 1A) | Connection Site: Phoenix 1A 275/66kV Offshore Substation -> Hawthorn Pit 400kV Substation | CHANGED | Morven Offshore Wind Limited | Hawthorn Pit 400kV Substation |  | 0 | 1500 | 1500 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001515
a0l4L0000005irpQAA | Neart Na Gaoithe Offshore Wind Farm | MW Connected: 0.0 -> 448.0; MW Increase / Decrease: 448.0 -> 0.0; MW Effective From: 01/06/2023 -> NULL; Project Status: Consents Approved -> Built | CHANGED | NEART NA GAOITHE OFFSHORE WIND LIMITED | Neart Na Gaoithe 220/66KV Offshore Substation |  | 448 | 0 | 448 |  | Built | Direct Connection | SPT | Wind Offshore | PRO-000273
a0l4L0000005ibmQAA | North East Offshore Wind Farm | Stage: NULL -> 1.0; MW Increase / Decrease: 2000.0 -> 600.0; Cumulative Total Capacity (MW): 2,000.00 MW -> 2,600.00 MW; MW Effective From: 31/10/2033 -> 31/03/2031; Project Number: PRO-001436 -> PRO-001436-1 | CHANGED | CALEDONIA OFFSHORE WIND FARM LIMITED | New Deer 2 400kV Substation | 1 | 0 | 600 | 600 | 2031-03-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001436-1
a0l4L0000005ibmQAA | North East Offshore Wind Farm | Stage: NULL -> 1.0; MW Increase / Decrease: 2000.0 -> 600.0; Cumulative Total Capacity (MW): 2,000.00 MW -> 2,600.00 MW; MW Effective From: 31/10/2033 -> 31/03/2031; Project Number: PRO-001436 -> PRO-001436-1 | CHANGED | CALEDONIA OFFSHORE WIND FARM LIMITED | New Deer 2 400kV Substation | 2 | 0 | 1400 | 2000 | 2032-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001436-2
a0l4L0000005iecQAA | Ossian 1 Offshore Wind Farm | Project Name: SSE Offshore 1 -> Ossian 1 Offshore Wind Farm; Customer Name: SSE RENEWABLES OFFSHORE WINDFARM HOLDINGS LIMITED -> Ossian Offshore Wind Farm Limited | CHANGED | Ossian Offshore Wind Farm Limited | SSE OFFSHORE 1 400/66KV OFFSHORE SUBSTATION |  | 0 | 1320 | 1320 | 2033-10-31 | Scoping | Direct Connection | SPT | Wind Offshore | PRO-001488
a0l4L0000005ieeQAA | Ossian 2 Offshore Wind Farm | Project Name: SSE Offshore 2 -> Ossian 2 Offshore Wind Farm; Customer Name: SSE RENEWABLES OFFSHORE WINDFARM HOLDINGS LIMITED -> Ossian Offshore Wind Farm Limited; HOST TO: SHET -> NGET | CHANGED | Ossian Offshore Wind Farm Limited | SSE OFFSHORE 2 220/66KV OFFSHORE SUBSTATION |  | 0 | 600 | 600 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001491
a0l4L0000005iedQAA | Ossian 3 Offshore Wind Farm | Project Name: SSE Offshore 3 -> Ossian 3 Offshore Wind Farm; Customer Name: SSE RENEWABLES OFFSHORE WINDFARM HOLDINGS LIMITED -> Ossian Offshore Wind Farm Limited | CHANGED | Ossian Offshore Wind Farm Limited | SSE Offshore 3 220/66kV Offshore Substation |  | 0 | 600 | 600 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001489
a0l4L0000005iaiQAA | OWF3 | Customer Name: SCOTTISHPOWER RENEWABLES (UK) LIMITED -> Marramwind Limited | CHANGED | Marramwind Limited | OWF3 275/66kV Offshore Substation | 1 | 0 | 1000 | 1000 | 2031-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001406-1
a0l4L0000005iaiQAA | OWF3 | Customer Name: SCOTTISHPOWER RENEWABLES (UK) LIMITED -> Marramwind Limited | CHANGED | Marramwind Limited | OWF3 275/66kV Offshore Substation | 2 | 0 | 2000 | 3000 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001406-2
a0l4L0000005iqSQAQ | OWPL Windfarm | MW Effective From: 31/10/2029 -> 31/12/2029 | CHANGED | OFFSHORE WIND POWER LIMITED | OWPL Windfarm Platform 220/66kV Offshore Substation | 1 | 0 | 750 | 750 | 2029-12-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-000568-1
a0l4L0000005iqSQAQ | OWPL Windfarm | MW Effective From: 31/10/2029 -> 31/12/2029 | CHANGED | OFFSHORE WIND POWER LIMITED | OWPL Windfarm Platform 220/66kV Offshore Substation | 2 | 0 | 1500 | 2250 | 2030-12-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-000568-2
a0l4L0000005idGQAQ | Pentland Floating Offshore Wind Farm | Connection Site: OWF-100 Substation -> Pentland Floating Offshore Wind Farm 132/66kV substation; MW Effective From: 31/08/2025 -> 31/10/2027 | CHANGED | HIGHLAND WIND LIMITED | Pentland Floating Offshore Wind Farm 132/66kV substation |  | 0 | 100 | 100 | 2027-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001472
a0l4L0000005iM5QAI | Petroc Extension Offshore Wind Farm | Customer Name: BLUEFLOAT ENERGY UK HOLDINGS LIMITED -> SCARABEN OFFSHORE WIND FARM LIMITED | CHANGED | SCARABEN OFFSHORE WIND FARM LIMITED | Alverdiscott 400kV Substation |  | 0 | 1000 | 1000 | 2036-12-06 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-002404
a0l4L0000005j1UQAQ | Petroc Offshore Wind Farm | Customer Name: BLUEFLOAT ENERGY UK HOLDINGS LIMITED -> SCARABEN OFFSHORE WIND FARM LIMITED | CHANGED | SCARABEN OFFSHORE WIND FARM LIMITED | Alverdiscott 400kV Substation |  | 0 | 300 | 300 | 2029-03-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001661
a0l4L0000005izKQAQ | Phoenix 1B Offshore Wind Farm | Customer Name: BP ALTERNATIVE ENERGY INVESTMENTS LIMITED -> Morven Offshore Wind Limited; Connection Site: Phoenix 1B 275/66kV Offshore Substation -> Branxton 400/132KV Substation | CHANGED | Morven Offshore Wind Limited | Branxton 400/132KV Substation |  | 0 | 1500 | 1500 | 2033-10-31 | Scoping | Direct Connection | SPT | Wind Offshore | PRO-001519
a0l4L0000005io1QAA | Rampion Extension Offshore Wind Farm | Connection Site: Rampion Offshore Wind Farm -> Bolney 400kV Substation | CHANGED | RAMPION EXTENSION DEVELOPMENT LIMITED | Bolney 400kV Substation |  | 0 | 1200 | 1200 | 2026-08-01 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000467
a0l4L0000005iulQAA | Scaraben Offshore Wind Farm | Customer Name: BLUEFLOAT ENERGY UK HOLDINGS LIMITED -> SCARABEN OFFSHORE WIND FARM LIMITED; Connection Site: Scaraben 132kV Offshore Substation -> Longside 132kV Substation | CHANGED | SCARABEN OFFSHORE WIND FARM LIMITED | Longside 132kV Substation |  | 0 | 100 | 100 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-002401
a0l4L0000005izYQAQ | Scira-Dudgeon Extension | Customer Name: EQUINOR NEW ENERGY LIMITED -> SHERINGHAM SHOAL AND DUDGEON EXTENSIONS PROJCO LIMITED; MW Effective From: 01/01/2029 -> 01/01/2030 | CHANGED | SHERINGHAM SHOAL AND DUDGEON EXTENSIONS PROJCO LIMITED | Norwich Main 400kV Substation | 1 | 0 | 719 | 719 | 2030-01-01 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000507-1
a0l4L0000005izYQAQ | Scira-Dudgeon Extension | Customer Name: EQUINOR NEW ENERGY LIMITED -> SHERINGHAM SHOAL AND DUDGEON EXTENSIONS PROJCO LIMITED; MW Effective From: 01/01/2029 -> 01/01/2030 | CHANGED | SHERINGHAM SHOAL AND DUDGEON EXTENSIONS PROJCO LIMITED | Norwich Main 400kV Substation | 2 | 0 | 231 | 950 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000507-2
a0l4L0000005izYQAQ | Scira-Dudgeon Extension | Customer Name: EQUINOR NEW ENERGY LIMITED -> SHERINGHAM SHOAL AND DUDGEON EXTENSIONS PROJCO LIMITED; MW Effective From: 01/01/2029 -> 01/01/2030 | CHANGED | SHERINGHAM SHOAL AND DUDGEON EXTENSIONS PROJCO LIMITED | Norwich Main 400kV Substation | 3 | 0 | 400 | 1350 | 2034-10-01 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000507-3
a0l4L0000005ipFQAQ | Seagreen 1 Offshore Wind Farm | Stage: 1.0 -> NULL; MW Connected: 0.0 -> 1075.0; MW Increase / Decrease: 10.0 -> 0.0; Cumulative Total Capacity (MW): 1,685.00 MW -> 1,075.00 MW; MW Effective From: 15/02/2022 -> NULL; Project Number: PRO-000527-1 -> PRO-000527 | CHANGED | Seagreen Wind Energy Limited | Tealing 275/33kV Substation |  | 1075 | 0 | 1075 |  | Built | Direct Connection | SHET | Wind Offshore | PRO-000527
a0l4L0000005izHQAQ | Seagreen Phase 1A | Project Name: Seagreen 1A Offshore Wind Farm -> Seagreen Phase 1A; MW Effective From: 01/04/2026 -> 01/04/2028 | CHANGED | SEAGREEN 1A LIMITED | Cockenzie 400/275kV |  | 0 | 500 | 500 | 2028-04-01 | Under Construction/Commissioning | Direct Connection | SPT | Wind Offshore | PRO-000703
a0l8e000000ez6zAAA | Sinclair Offshore Wind Farm | Connection Site: Peterhead 400kV Substation -> Longside 132kV Substation | CHANGED | SINCLAIR OFFSHORE WIND FARM LIMITED | Longside 132kV Substation |  | 0 | 100 | 100 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-003790
a0l4L0000005imVQAQ | Sofia Offshore Wind Farm | Stage: 1.0 -> NULL; MW Increase / Decrease: 132.0 -> 1320.0; Cumulative Total Capacity (MW): 1,452.00 MW -> 1,320.00 MW; MW Effective From: 01/09/2024 -> 30/01/2026; Project Status: Consents Approved -> Scoping; Project Number: PRO-000404-1 -> PRO-000404 | CHANGED | SOFIA OFFSHORE WIND FARM LIMITED | Dogger Bank 220kV Offshores |  | 0 | 1320 | 1320 | 2026-01-30 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000404
a0l4L0000005iNeQAI | Spiorad Na Mara Offshore Wind Farm | MW Increase / Decrease: 740.0 -> 900.0; Cumulative Total Capacity (MW): 740.00 MW -> 900.00 MW; MW Effective From: 31/10/2030 -> 31/12/2030 | CHANGED | SPIORAD NA MARA LIMITED | NPI C 220/66KV OFFSHORE SUBSTATION |  | 0 | 900 | 900 | 2030-12-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001642
a0l4L0000005iwQQAQ | SSE Offshore 4 | Customer Name: SSE RENEWABLES OFFSHORE WINDFARM HOLDINGS LIMITED -> Ossian Offshore Wind Farm Limited | CHANGED | Ossian Offshore Wind Farm Limited | Cousland 400kV |  | 0 | 1008 | 1008 | 2033-10-31 | Scoping | Direct Connection | SPT | Wind Offshore | PRO-002145
a0l4L0000005izNQAQ | Stromar Offshore Windfarm | Project Name: Cygnus Offshore Windfarm -> Stromar Offshore Windfarm; Customer Name: RENANTIS UK LIMITED -> Stromar Offshore Wind Farm Limited; Connection Site: Cygnus 220/66kV Offshore Substation -> New Deer 2 400kV Substation; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 1,000.00 MW -> 2,500.00 MW; Project Number: PRO-001530 -> PRO-001530-1 | CHANGED | Stromar Offshore Wind Farm Limited | New Deer 2 400kV Substation | 1 | 0 | 1000 | 1000 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001530-1
a0l4L0000005izNQAQ | Stromar Offshore Windfarm | Project Name: Cygnus Offshore Windfarm -> Stromar Offshore Windfarm; Customer Name: RENANTIS UK LIMITED -> Stromar Offshore Wind Farm Limited; Connection Site: Cygnus 220/66kV Offshore Substation -> New Deer 2 400kV Substation; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 1,000.00 MW -> 2,500.00 MW; Project Number: PRO-001530 -> PRO-001530-1 | CHANGED | Stromar Offshore Wind Farm Limited | New Deer 2 400kV Substation | 2 | 0 | 500 | 1500 | 2035-12-31 | Scoping | Direct Connection | SHET | Wind Offshore | PRO-001530-2
a0l4L0000005iy6QAA | Torridge Offshore Wind Farm | Customer Name: UK MAINSTREAM RENEWABLE POWER LIMITED -> GWYNT GLAS OFFSHORE WIND FARM LIMITED | CHANGED | GWYNT GLAS OFFSHORE WIND FARM LIMITED | Alverdiscott 400kV Substation |  | 0 | 1500 | 1500 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001917
a0l4L0000005iZlQAI | Valorous Offshore Wind Farm | Customer Name: BLUE GEM WIND LIMITED -> Blue Gem Wind Limited; MW Effective From: 02/04/2029 -> 31/10/2031 | CHANGED | Blue Gem Wind Limited | Pembroke 400kV Substation |  | 0 | 300 | 300 | 2031-10-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-001383
a0l4L0000005izdQAA | Vanguard East | Connection Site: Necton 400kV Substation -> Vanguard East 275/66kV Offshore Substation | CHANGED | Norfolk Vanguard East Ltd | Vanguard East 275/66kV Offshore Substation | 1 | 0 | 400 | 400 | 2028-04-01 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000580-1
a0l4L0000005izdQAA | Vanguard East | Connection Site: Necton 400kV Substation -> Vanguard East 275/66kV Offshore Substation | CHANGED | Norfolk Vanguard East Ltd | Vanguard East 275/66kV Offshore Substation | 2 | 0 | 920 | 1320 | 2028-12-31 | Scoping | Direct Connection | NGET | Wind Offshore | PRO-000580-2

## Pot 1 (Onshore-Solar)
TEC Register Comparison: Pot 1 (Onshore-Solar)
Version A: tec-register-2024-12-06.csv | Version B: tec-register-2025-12-18.csv
SUMMARY OF PROJECT CHANGES:
Metric | Value
Projects Added (in B only) | 47
Projects Removed (in A only) | 0
Projects with Field Change (excluding Added/Removed) | 127
--- | ---
Capacity Added (MW) | 4,235.97
Capacity Removed (MW) | 0.00
--- DETAILED PROJECT CHANGES ---
'ADDED' and 'CHANGED' rows show Version B (Latest) data.
'REMOVED' rows show Version A (Old) data.
Project ID | Project Name | Changes Made | Change_Type | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project Number | Gate
a0lJ9000000POFuIAO | Allt Domhain Wind Farm | NEWLY ADDED PROJECT | ADDED | ENERGYFARM ALLT DOMHAIN LTD | Carradale 1 GSP |  | 0 | 64.8 | 64.8 | 2035-10-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-006015
a0l8e0000010wXBAAY | Appin Wind Farm | NEWLY ADDED PROJECT | ADDED | Appin Wind Farm Limited | Glenglass 132kV Substation |  | 0 | 66 | 66 | 2031-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-002661
a0l8e000000f5BiAAI | Beinn an Tuirc 1 | NEWLY ADDED PROJECT | ADDED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Beinn an Tuirc Substation |  | 0 | 95.2 | 95.2 | 2034-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003918
a0lJ9000000POVwIAO | Beinneun 2 Windfarm | NEWLY ADDED PROJECT | ADDED | BEINNEUN 2 LIMITED | Beinneun Windfarm 2 |  | 0 | 144 | 144 | 2037-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-006053
a0lJ9000000PDkoIAG | Blair Hill Wind Farm | NEWLY ADDED PROJECT | ADDED | Renewable Energy Systems Limited | Craigenputtlock 400/132 kV Substation |  | 0 | 99 | 99 | 2036-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-004994
a0l8e0000012eIpAAI | Calderdale Wind Farm 240 MW | NEWLY ADDED PROJECT | ADDED | CALDERDALE WIND FARM LTD | Rochdale GSP |  | 0 | 170 | 170 | 2037-10-30 | Scoping | Embedded | NGET | Wind Onshore | PRO-004365
a0l8e0000012kqcAAA | Causeymire 2 Wind Farm | NEWLY ADDED PROJECT | ADDED | HEADWIND DEVELOPMENT SERVICES LIMITED | Mybster 4 GSP |  | 0 | 39.6 | 39.6 | 2034-10-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-004778
a0l8e0000012kpUAAQ | D&G 2 | NEWLY ADDED PROJECT | ADDED | D&G 2 Limited | Glenluce 132/33kV |  | 0 | 60 | 60 | 2031-08-29 | Scoping | Embedded | SPT | Wind Onshore | PRO-004772
a0l8e0000012kkvAAA | Clashindarroch Windfarm Extension | NEWLY ADDED PROJECT | ADDED | CLASHINDARROCH WINDFARM EXTENSION LIMITED | Clashindarroch Windfarm Extension 132kV Substation |  | 0 | 145.2 | 145.2 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-004769
a0l8e000000evgLAAQ | Coldstream Solar PV Plant | NEWLY ADDED PROJECT | ADDED | Conrad Energy (Developments) II Limited | Eccles GSP |  | 0 | 40.56 | 40.56 | 2031-07-31 | Scoping | Embedded | SPT | PV Array (Photo Voltaic/solar) | PRO-003635
a0lJ9000000PDyOIAW | Costa Head | NEWLY ADDED PROJECT | ADDED | COSTA HEAD WIND FARM LIMITED | Finstown (Orkney) GSP |  | 0 | 16.32 | 16.32 | 2029-04-06 | Scoping | Embedded | SHET | Wind Onshore | PRO-005102
a0lJ9000000POQKIA4 | Craigdow Hill Wind Farm | NEWLY ADDED PROJECT | ADDED | ABEI ENERGY LIMITED | Maybole GSP |  | 0 | 38.4 | 38.4 | 2032-10-31 | Scoping | Embedded | SPT | Wind Onshore | PRO-006036
a0l8e0000010wlKAAQ | Craighead Wind Farm | NEWLY ADDED PROJECT | ADDED | GALILEO 02 LIMITED | Westfield 132/33kV |  | 0 | 77 | 77 | 2032-10-29 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-002821
a0l8e0000012jL5AAI | Craigneil Wind Farm | NEWLY ADDED PROJECT | ADDED | ESB ASSET DEVELOPMENT UK LIMITED | Fetteresso GSP |  | 0 | 42 | 42 | 2030-10-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-004670
a0l8e000001HrDhAAK | Creag Dhubh | NEWLY ADDED PROJECT | ADDED | MUIRDEN ENERGY LLP | Clachan 2 GSP |  | 0 | 38.34 | 38.34 | 2030-10-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-004206
a0lJ9000000POjyIAG | Crookedstone PV | NEWLY ADDED PROJECT | ADDED | Enviromena Project Management UK Limited | Strathaven GSP 33kV |  | 0 | 49.9 | 49.9 | 2032-10-31 | Scoping | Embedded | SPT | PV Array (Photo Voltaic/solar) | PRO-006119
a0lJ9000000PFobIAG | Derwent Solar 2 | NEWLY ADDED PROJECT | ADDED | Derwent Solar 2 Limited | Osbaldwick GSP |  | 0 | 200 | 200 | 2039-10-31 | Scoping | Embedded | NGET | PV Array (Photo Voltaic/solar) | PRO-005908
a0l8e0000012hmYAAQ | Fauldielaw | NEWLY ADDED PROJECT | ADDED | Renewable Energy Systems Limited | Arbroath GSP |  | 0 | 49.9 | 49.9 | 2032-10-31 | Scoping | Embedded | SHET | PV Array (Photo Voltaic/solar) | PRO-004503
a0lJ9000000POkIIAW | Forsinain Wind Farm | NEWLY ADDED PROJECT | ADDED | Forsinain Forest Wind Farm Limited | Connagill 132kV Substation |  | 0 | 99 | 99 | 2037-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-006123
a0lJ9000000PGEgIAO | Gladsmuir Wind Farm | NEWLY ADDED PROJECT | ADDED | WIND ESTATE (UK) LIMITED | Harburn 132/33kV Grid Supply Point Substation |  | 0 | 43 | 43 | 2032-10-29 | Scoping | Embedded | SPT | Wind Onshore | PRO-005915
a0lJ9000000POPHIA4 | Glasvaar | NEWLY ADDED PROJECT | ADDED | E Power Limited | Craig Murrail GSP |  | 0 | 36 | 36 | 2037-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-006025
a0l8e0000012ggkAAA | Glenmore | NEWLY ADDED PROJECT | ADDED | AEUK WIND PROJECT II LTD | Edinbane 132/33kV Substation |  | 0 | 39.6 | 39.6 | 2034-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-004445
a0l8e0000012hwRAAQ | Grayside Wind Farm | NEWLY ADDED PROJECT | ADDED | GRAYSIDE WF LTD | Grayside 132/33kV Substation |  | 0 | 108 | 108 | 2037-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-004563
a0lJ9000000PDyEIAW | Hesta Head | NEWLY ADDED PROJECT | ADDED | HESTA HEAD WIND FARM LIMITED | Finstown (Orkney) GSP |  | 0 | 20.4 | 20.4 | 2029-04-06 | Scoping | Embedded | SHET | Wind Onshore | PRO-005100
a0lJ9000000blQUIAY | High Brenfield 1 | NEWLY ADDED PROJECT | ADDED | High Brenfield Wind Farm Limited | High Brenfield 1 GSP |  | 0 | 52.8 | 52.8 | 2034-10-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-004875
a0lJ9000000blQZIAY | High Brenfield 2 | NEWLY ADDED PROJECT | ADDED | High Brenfield Wind Farm Limited | Craig Murrail GSP |  | 0 | 20.4 | 20.4 | 2034-10-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-004876
a0lJ9000000PNpTIAW | Hoolan Hills Renewable Energy Park | NEWLY ADDED PROJECT | ADDED | RIDGE CLEAN ENERGY LTD | Holm Hill 132kV Substation |  | 0 | 66 | 66 | 2037-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-006001 | 1
a0lJ9000000PEBHIA4 | Huntington Solar PV | NEWLY ADDED PROJECT | ADDED | EDF ENERGY RENEWABLES LIMITED | West Anglia Connection Node D 400kV Substation |  | 0 | 240 | 240 | 2037-10-31 | Scoping | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-005118 | 1
a0lJ9000000PDwDIAW | KENLEY HOUSE SOLAR PARK | NEWLY ADDED PROJECT | ADDED | BOOM DEVELOPMENTS LTD | Creyke Beck GSP |  | 0 | 150 | 150 | 2039-10-30 | Scoping | Embedded | NGET | PV Array (Photo Voltaic/solar) | PRO-005078
a0lJ9000000PNKlIAO | Kenwick Solar | NEWLY ADDED PROJECT | ADDED | ANESCO LIMITED | Shrewsbury 400kV Substation |  | 0 | 430.85 | 430.85 | 2037-10-31 | Scoping | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-005989
a0lJ9000000POjPIAW | Killeal | NEWLY ADDED PROJECT | ADDED | ABEI ENERGY LIMITED | Newton Stewart GSP |  | 0 | 72.6 | 72.6 | 2036-10-31 | Scoping | Embedded | SPT | Wind Onshore | PRO-006112
a0lJ9000000POB6IAO | Killean Wind Farm | NEWLY ADDED PROJECT | ADDED | Renewable Energy Systems Limited | CARRADALE 3 GSP |  | 0 | 60 | 60 | 2034-10-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-006009
a0lJ9000000blmSIAQ | Middlewick Wind | NEWLY ADDED PROJECT | ADDED | DENGIE MARSHES WIND FARM LIMITED | Rayleigh Main GSP |  | 0 | 120 | 120 | 2034-10-31 | Scoping | Embedded | NGET | Wind Onshore | PRO-004940
a0l8e000000f7gMAAQ | Millennium East | NEWLY ADDED PROJECT | ADDED | Renantis UK Limited | Fort Augustus GSP/New Fort Augustus GSP |  | 0 | 49.9 | 49.9 | 2035-10-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-004010
a0l8e0000012hmTAAQ | North Ray Solar Farm 2 | NEWLY ADDED PROJECT | ADDED | NORTH RAY SOLAR FARM 2 LTD | Grimsby West GSP |  | 0 | 180 | 180 | 2035-10-30 | Scoping | Embedded | NGET | PV Array (Photo Voltaic/solar) | PRO-004502
a0l8e0000012kptAAA | Novar 2 Wind Farm | NEWLY ADDED PROJECT | ADDED | HEADWIND DEVELOPMENT SERVICES LIMITED | Alness GSP |  | 0 | 43.2 | 43.2 | 2032-10-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-004775
a0lJ9000000blsMIAQ | Peninsula Energy Park | NEWLY ADDED PROJECT | ADDED | Renantis UK Limited | Taynuilt GSP |  | 0 | 249.9 | 249.9 | 2035-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-004961
a0l8e000000eybvAAA | Pollie Hill Wind Farm | NEWLY ADDED PROJECT | ADDED | POLLIE HILL WIND FARM LIMITED | POLLIE HILL WIND FARM 132KV SUBSTATION |  | 0 | 92.4 | 92.4 | 2031-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003767
a0lJ9000000POuiIAG | Ruith Cnoc | NEWLY ADDED PROJECT | ADDED | Ruith Cnoc Wind Farm Limited | Dalchork 132kV Substation |  | 0 | 158.4 | 158.4 | 2037-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-006147
a0lJ9000000blamIAA | Shire End Solar Farm | NEWLY ADDED PROJECT | ADDED | QAIR SCOTLAND LIMITED | Abernethy GSP |  | 0 | 20 | 20 | 2033-10-31 | Scoping | Embedded | SHET | PV Array (Photo Voltaic/solar) | PRO-004902
a0lJ9000000blMrIAI | Statkraft SEWF | NEWLY ADDED PROJECT | ADDED | Statkraft UK Ltd | Orrin GSP |  | 0 | 100.8 | 100.8 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-004828 | 1
a0l8e0000012hoyAAA | Stoneyfield | NEWLY ADDED PROJECT | ADDED | WIND 2 LIMITED | Rothienorman GSP |  | 0 | 15 | 15 | 2030-09-30 | Scoping | Embedded | SHET | Wind Onshore | PRO-004531
a0lJ9000000POkcIAG | Stoneygroves PV | NEWLY ADDED PROJECT | ADDED | Enviromena Project Management UK Limited | Charleston GSP 132/33kV |  | 0 | 20 | 20 | 2031-10-30 | Scoping | Embedded | SHET | PV Array (Photo Voltaic/solar) | PRO-006127
a0lJ9000000POfgIAG | The Drum Wind Farm | NEWLY ADDED PROJECT | ADDED | WIND ESTATE (UK) LIMITED | The Drum 132KV Substation |  | 0 | 57.6 | 57.6 | 2037-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-006069
a0lJ9000000PNJDIA4 | Tioram Wind Farm | NEWLY ADDED PROJECT | ADDED | Invenergy Development UK Ltd | CARRADALE 3 GSP |  | 0 | 160 | 160 | 2037-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-005973
a0l8e000000TPEZAA4 | Vale of Leven Wind Farm | NEWLY ADDED PROJECT | ADDED | Vale of Leven Wind Farm Limited | Vale of Leven 132kV substation |  | 0 | 72 | 72 | 2033-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-003214
a0lJ9000000POfqIAG | Windy Standard 1 Repower | NEWLY ADDED PROJECT | ADDED | FRED. OLSEN RENEWABLES LIMITED | Dun Hill 132/33kV |  | 0 | 21.9 | 21.9 | 2031-06-30 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-006071
a0l4L0000005iREQAY | Artfield Forest Windfarm | REMOVED PROJECT | REMOVED | ARTFIELD FOREST WIND FARM LTD | Newton Stewart GSP |  | 0 | 67.2 | 67.2 | 2026-05-01 | Scoping | Embedded | SPT | Wind Onshore | PRO-001310
a0l4L0000005iSOQAY | Braelangwell Wind Farm | REMOVED PROJECT | REMOVED | WIND DEVELOPMENT HOLDINGS LIMITED | Shin GSP |  | 0 | 68 | 68 | 2028-02-01 | Awaiting Consents | Embedded | SHET | Wind Onshore | PRO-000916
a0l4L0000005inKQAQ | Costa Head Wind Farm | REMOVED PROJECT | REMOVED | COSTA HEAD WIND FARM LIMITED | Costa Head 132/33kV Substation |  | 0 | 20.4 | 20.4 | 2028-10-30 | Consents Approved | Direct Connection | SHET | Wind Onshore | PRO-000104
a0l8e0000012ezbAAA | Dalswinton WindFarm Extension | REMOVED PROJECT | REMOVED | DALSWINTON WINDFARM (SCOTLAND) LIMITED | Dumfries 132/33kV |  | 0 | 38.4 | 38.4 | 2029-09-30 | Scoping | Embedded | SPT | Wind Onshore | PRO-004393
a0l4L0000005iyXQAQ | Hesta Head Wind Farm | REMOVED PROJECT | REMOVED | HESTA HEAD WIND FARM LIMITED | Hesta Head 132/33kV Substation |  | 0 | 20.4 | 20.4 | 2028-10-30 | Consents Approved | Direct Connection | SHET | Wind Onshore | PRO-000308
a0l4L0000005ihaQAA | Highland Wind Farm | REMOVED PROJECT | REMOVED | AMPYR ENERGY UK DEVELOPMENT LIMITED | Tomatin 275/132 kV Substation |  | 0 | 168.2 | 168.2 | 2028-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-001747
a0l4L0000005igoQAA | Lochgoin Solar Farm | REMOVED PROJECT | REMOVED | TURBINE MARKETING SPV LIMITED | Whitelee Extension 275/33kV |  | 0 | 89 | 89 | 2027-09-29 | Scoping | Direct Connection | SPT | PV Array (Photo Voltaic/solar) | PRO-001107
a0l8e000000TPDCAA4 | Summerston PV 50MW | REMOVED PROJECT | REMOVED | Bluestone Energy Ltd | Killermont 132/33kV |  | 0 | 50 | 100 | 2031-06-30 | Scoping | Embedded | SPT | PV Array (Photo Voltaic/solar) | PRO-003199
a0l4L0000005ikeQAA | Waternish Wind Farm Substaion | REMOVED PROJECT | REMOVED | WIND DEVELOPMENT HOLDINGS LIMITED | Waternish Wind Farm 12KV Substation |  | 0 | 81.6 | 81.6 | 2034-04-30 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-002295
a0l4L0000005iiYQAQ | Achany Extension Wind Farm | Customer Name: SSE GENERATION LIMITED -> SSE Generation Limited; Connection Site: Shin GSP -> ACHANY EXTENSION WIND FARM 132/33KV Substation | CHANGED | SSE Generation Limited | ACHANY EXTENSION WIND FARM 132/33KV Substation |  | 0 | 105 | 105 | 2028-03-30 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-001555
a0l4L0000005iphQAA | Aikengall IIA Wind Farm | Project Name: AIKENGALL II WIND FARM -> Aikengall IIA Wind Farm | CHANGED | AIK2A SUSTAINABLE ENERGY LTD | Wester Dod 132kV |  | 81.2 | 0 | 81.2 |  | Built | Direct Connection | SPT | Wind Onshore | PRO-000559
a0l4L0000005ixHQAQ | Arecleoch Extension Windfarm | Project Name: Arecleoch Windfarm Extension -> Arecleoch Extension Windfarm | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Arecleoch 132/33kV |  | 0 | 72.8 | 72.8 | 2026-08-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001111
a0l8e0000011zPNAAY | Artfield Forest Wind Farm | Project Status: Scoping -> Consents Approved | CHANGED | ARTFIELD FOREST WIND FARM LTD | Artfield Forest Wind Farm 132kV Substation |  | 0 | 85.8 | 85.8 | 2030-06-28 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-003578
a0l4L0000005iyaQAA | Beaw Field Wind Farm | MW Increase / Decrease: 72.0 -> 102.0; Cumulative Total Capacity (MW): 72.00 MW -> 102.00 MW; MW Effective From: 30/11/2028 -> 29/10/2032 | CHANGED | BEAW FIELD SHETLAND LIMITED | Beaw Field 132/33kV Substation |  | 0 | 102 | 102 | 2032-10-29 | Consents Approved | Direct Connection | SHET | Wind Onshore | PRO-000026
a0l4L0000005ixnQAA | Beechgreen Energyfarm | MW Connected: 49.9 -> 49.995; Cumulative Total Capacity (MW): 49.90 MW -> 50.00 MW | CHANGED | BEECHGREEN ENERGYFARM LIMITED | Burwell Main 400kV Substation |  | 49.995 | 0 | 50 |  | Built | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-001018
a0l4L0000005ilaQAA | Benbrack Wind Farm | Customer Name: Benbrack Wind Farm Limited -> BENBRACK WIND FARM LIMITED; MW Connected: 0.0 -> 72.0; MW Increase / Decrease: 72.0 -> 0.0; MW Effective From: 30/01/2025 -> NULL; Project Status: Awaiting Consents -> Built | CHANGED | BENBRACK WIND FARM LIMITED | Benbrack Wind Farm 132/33kV Substation |  | 72 | 0 | 72 |  | Built | Direct Connection | SPT | Wind Onshore | PRO-000032
a0l4L0000005iUGQAY | Berryburn Extension Wind Farm | MW Effective From: 31/10/2024 -> 30/11/2025; Project Status: Scoping -> Consents Approved | CHANGED | BB2 WIND FARM LIMITED | Berry Burn GSP |  | 0 | 43.2 | 43.2 | 2025-11-30 | Consents Approved | Embedded | SHET | Wind Onshore | PRO-001558
a0l4L0000005ilnQAA | Bhlaraidh Extension Wind Farm | Customer Name: SSE GENERATION LIMITED -> SSE Generation Limited; MW Effective From: 01/04/2026 -> 17/08/2029 | CHANGED | SSE Generation Limited | Bhlaraidh 132/33kV Substation |  | 0 | 100.8 | 100.8 | 2029-08-17 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-000383
a0l4L0000005ilbQAA | Bhlaraidh Wind Farm | Customer Name: SSE GENERATION LIMITED -> SSE Generation Limited | CHANGED | SSE Generation Limited | Bhlaraidh 132/33kV Substation |  | 108 | 0 | 108 |  | Built | Direct Connection | SHET | Wind Onshore | PRO-000034
a0l4L0000005itaQAA | Blarghour Wind | MW Increase / Decrease: 73.1 -> 67.2; Cumulative Total Capacity (MW): 73.10 MW -> 67.20 MW; MW Effective From: 31/10/2027 -> 01/04/2029 | CHANGED | BLARGHOUR WIND FARM LIMITED | Blarghour Substation |  | 0 | 67.2 | 67.2 | 2029-04-01 | Consents Approved | Direct Connection | SHET | Wind Onshore | PRO-000398
a0l8e0000011yCAAAY | Bradford Solar Farm | Customer Name: SOLARFOUR LTD -> SolarFour Ltd; Connection Site: Ironbridge 400kV Substation -> Staffordshire Connection Node A 400kV Substation | CHANGED | SolarFour Ltd | Staffordshire Connection Node A 400kV Substation |  | 0 | 960 | 960 | 2033-10-31 | Scoping | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-003511
a0l4L0000005ilQQAQ | Broken Cross Windfarm | MW Connected: 48.0 -> 43.2; MW Increase / Decrease: 0.0 -> 4.8; MW Effective From: NULL -> 01/04/2026 | CHANGED | BROKEN CROSS WIND FARM LIMITED | Broken Cross 132/33kV |  | 43.2 | 4.8 | 48 | 2026-04-01 | Built | Direct Connection | SPT | Wind Onshore | PRO-000395
a0l8e000001HoYjAAK | Brown Rig Wind Farm | Customer Name: SSE RENEWABLES SERVICES (UK) LIMITED -> SSE Renewables Services (UK) Limited | CHANGED | SSE Renewables Services (UK) Limited | Hawick 132kV Substation |  | 0 | 114 | 114 | 2033-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-004083
a0l4L0000005iXXQAY | Bryn Tilti | MW Effective From: 04/02/2027 -> 19/07/2028; Agreement Type: Direct Connection -> Embedded | CHANGED | RHIWLAS ENERGY PARK LIMITED | Chirk GSP |  | 0 | 106 | 106 | 2028-07-19 | Scoping | Embedded | NGET | Wind Onshore | PRO-001586
a0l4L0000005iUHQAY | Builth Wells | Agreement Type: Direct Connection -> Embedded | CHANGED | ABEREDW ENERGY PARK LIMITED | Pont Abraham GSP |  | 0 | 133 | 133 | 2026-10-31 | Scoping | Embedded | NGET | Wind Onshore | PRO-001564
a0l4L0000005iRLQAY | Cairnmore Hill Wind Farm | Customer Name: Renewable Energy Systems Limited -> Cairnmore Hill Energy Limited; Connection Site: Thurso South GSP -> Thurso South 132/33kV GSP Substation | CHANGED | Cairnmore Hill Energy Limited | Thurso South 132/33kV GSP Substation |  | 0 | 36 | 36 | 2028-05-31 | Awaiting Consents | Embedded | SHET | Wind Onshore | PRO-001304
a0l8e0000012kcnAAA | Calderdale Wind Farm 312MW | Connection Site: Calderdale Wind Farm 275kV Substation -> Leeds North Connection Node B 400kV Substation | CHANGED | CALDERDALE WIND FARM LTD | Leeds North Connection Node B 400kV Substation |  | 0 | 312 | 312 | 2035-10-30 | Scoping | Direct Connection | NGET | Wind Onshore | PRO-004714
a0l4L0000005isGQAQ | Caple Rig [formerly Faw Side Community Wind Farm] | Project Name: Faw Side Community Wind Farm -> Caple Rig [formerly Faw Side Community Wind Farm]; Connection Site: Faw Side Community Wind Farm Substation -> Caple Rig 132kV Substation; MW Effective From: 31/10/2025 -> 07/09/2029; Project Status: Awaiting Consents -> Scoping | CHANGED | CWP Energy Limited | Caple Rig 132kV Substation |  | 0 | 250 | 250 | 2029-09-07 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000297
a0l4L0000005iMQQAY | Car Duibh Wind Farm | Project Status: Scoping -> Awaiting Consents | CHANGED | CAR DUIBH WIND FARM LIMITED | Car Duibh 275kV Substation |  | 0 | 99 | 99 | 2034-10-31 | Awaiting Consents | Direct Connection | SHET | Wind Onshore | PRO-002342
a0l4L0000005ivTQAQ | Carn Fearna Wind Farm | Customer Name: STATKRAFT UK LTD -> Carn Fearna Wind Farm Limited; MW Effective From: 30/06/2029 -> 30/06/2030 | CHANGED | Carn Fearna Wind Farm Limited | Carn Fearna Wind Farm 132/33kV Substation |  | 0 | 85 | 85 | 2030-06-30 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-002231
a0l4L0000005iVEQAY | Carnedd Wen Wind Farm | Customer Name: Npower Renewables Ltd -> CARNEDD WEN WIND FARM LIMITED; MW Effective From: 01/04/2026 -> 31/10/2030 | CHANGED | CARNEDD WEN WIND FARM LIMITED | Mid Wales West 132kV Substation |  | 0 | 150 | 150 | 2030-10-31 | Scoping | Embedded | NGET | Wind Onshore | PRO-000090
a0l4L0000005iaWQAQ | Carrick Wind Farm | MW Effective From: 28/02/2029 -> 01/04/2030 | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Carrick Wind Farm Substation |  | 0 | 84 | 84 | 2030-04-01 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001026
a0l8e000000f5XxAAI | Castlemilk 1 | Connection Site: Moffat 132/33kV -> Castlemilk 400kV Substation | CHANGED | Queequeg Renewables Ltd | Castlemilk 400kV Substation |  | 0 | 300 | 300 | 2036-10-31 | Scoping | Direct Connection | SPT | PV Array (Photo Voltaic/solar) | PRO-003932
a0l8e000000TPK3AAO | Ceislein Wind Farm | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited | CHANGED | RWE Renewables UK Onshore Wind Limited | Ceislien Wind Farm |  | 0 | 85.8 | 85.8 | 2031-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003256
a0l4L0000005inCQAQ | Chirmorie Wind Farm | MW Increase / Decrease: 80.0 -> 91.0; Cumulative Total Capacity (MW): 80.00 MW -> 91.00 MW; MW Effective From: 30/04/2026 -> 09/10/2026 | CHANGED | CHIRMORIE WIND FARM LIMITED | Chirmorie 132/33kV Substation |  | 0 | 91 | 91 | 2026-10-09 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000094
a0l4L0000005iZoQAI | Cloich Forest Wind Farm | Connection Site: Cloiche 132kV Substation -> Cloich 132kV Substation; HOST TO: SHET -> SPT | CHANGED | EDF ENERGY RENEWABLES LIMITED | Cloich 132kV Substation |  | 0 | 67.2 | 67.2 | 2029-07-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001387
a0l4L0000005ilxQAA | Cloiche Wind Farm | Customer Name: SSE GENERATION LIMITED -> SSE Generation Limited; Connection Site: Cloiche 132kV Substation -> Cloich 132kV Substation; MW Effective From: 31/07/2027 -> 01/02/2028 | CHANGED | SSE Generation Limited | Cloich 132kV Substation |  | 0 | 200 | 200 | 2028-02-01 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-000425
a0l8e0000010wbPAAQ | Coille Beith Wind Farm | Project Name: Oykel Wind Farm -> Coille Beith Wind Farm; Customer Name: STATKRAFT UK LTD -> COILLE BEITH WIND FARM LIMITED | CHANGED | COILLE BEITH WIND FARM LIMITED | Oykel Wind Farm 132kV Substation |  | 0 | 79.2 | 79.2 | 2032-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-002711
a0l4L0000005if2QAA | Cornharrow Wind Farm | Connection Site: Quantans Hill 132kV -> Quantans Hill 132kV Substation; MW Effective From: 31/10/2027 -> 31/10/2030 | CHANGED | ENERGYFARM UK CORNHARROW LLP | Quantans Hill 132kV Substation |  | 0 | 50 | 50 | 2030-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001741
a0l4L0000005iNoQAI | Correen Hills Wind Farm | Project Name: Littlewoods Wind Farm -> Correen Hills Wind Farm; Connection Site: Littlewoods Wind Farm 132/33kV Substation -> Correen Hills Wind Farm 132kV Substation; MW Effective From: 31/08/2028 -> 30/09/2031 | CHANGED | EDF ENERGY RENEWABLES LIMITED | Correen Hills Wind Farm 132kV Substation |  | 0 | 68.4 | 68.4 | 2031-09-30 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-001825
a0l4L0000005imGQAQ | Corriegarth 2 Wind Farm | MW Effective From: 31/07/2026 -> 31/07/2027 | CHANGED | CORRIEGARTH 2 WIND FARM LIMITED | Corriegarth 132/33kV substation |  | 0 | 70 | 70 | 2027-07-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-000420
a0l4L0000005iPSQAY | Coupar Solar Farm | MW Effective From: 31/10/2025 -> 30/04/2027 | CHANGED | COUPAR TWO LIMITED | Coupar Angus GSP |  | 0 | 49.9 | 49.9 | 2027-04-30 | Scoping | Embedded | SHET | PV Array (Photo Voltaic/solar) | PRO-001862
a0l4L0000005iyhQAA | Craig Watch Wind Farm | MW Effective From: 30/06/2028 -> 15/05/2031; Project Status: Scoping -> Awaiting Consents | CHANGED | Craig Watch Wind Farm Limited | Craig Watch Substation |  | 0 | 72.6 | 72.6 | 2031-05-15 | Awaiting Consents | Direct Connection | SHET | Wind Onshore | PRO-001877
a0l8e000000f4yFAAQ | Creachan Wind Farm | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited; MW Effective From: 30/07/2029 -> 31/10/2030 | CHANGED | RWE Renewables UK Onshore Wind Limited | Creachan Wind Farm 132/33kV Substation |  | 0 | 79.2 | 79.2 | 2030-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003906
a0l8e000000f4w9AAA | Cruach Bhreac Wind Farm | Customer Name: STATKRAFT UK LTD -> Statkraft UK Ltd; Connection Site: Craig Murrail GSP -> Craig Murrail 275kV Substation; Gate: -> 1.0 | CHANGED | Statkraft UK Ltd | Craig Murrail 275kV Substation |  | 0 | 100.8 | 100.8 | 2034-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003879 | 1
a0l4L0000005ipMQAQ | Crystal Rig IV Wind Farm | Connection Site: Crystal Rig 132/33kV -> Crystal Rig 400kV substation; MW Effective From: 30/06/2024 -> 13/10/2025 | CHANGED | CRYSTAL RIG IV LIMITED | Crystal Rig 400kV substation |  | 0 | 48.2 | 48.2 | 2025-10-13 | Under Construction/Commissioning | Direct Connection | SPT | Wind Onshore | PRO-000520
a0l4L0000005ix7QAA | Cumberhead West Wind Farm | MW Effective From: 01/11/2024 -> 31/07/2025 | CHANGED | CUMBERHEAD WEST WIND FARM LTD. | Cumberhead 33kV |  | 0 | 114 | 114 | 2025-07-31 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | PRO-000423
a0l4L0000005iqVQAQ | Daer Wind Farm | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited; Connection Site: Daer Windfarm 132/33kV -> Daer Wind Farm 132/33kV; MW Effective From: 14/07/2027 -> 01/08/2028 | CHANGED | RWE Renewables UK Onshore Wind Limited | Daer Wind Farm 132/33kV |  | 0 | 96 | 96 | 2028-08-01 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000565
a0l4L0000005ibPQAQ | Dell Wind Farm | MW Effective From: 31/07/2027 -> 01/04/2030 | CHANGED | DELL WIND FARM LIMITED | Dell 132kV Substation |  | 0 | 49.8 | 49.8 | 2030-04-01 | Consents Approved | Direct Connection | SHET | Wind Onshore | PRO-001012
a0l4L0000005imEQAQ | Dersalloch Wind Farm | MW Increase / Decrease: 11.0 -> 0.0; Cumulative Total Capacity (MW): 80.00 MW -> 69.00 MW; MW Effective From: 31/10/2027 -> NULL | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Dersalloch 132/33kV |  | 69 | 0 | 69 |  | Built | Direct Connection | SPT | Wind Onshore | PRO-000060
a0l4L0000005iUEQAY | Drax Solar | Customer Name: BOOM DEVELOPMENTS LTD -> East Yorkshire Solar Farm Limited | CHANGED | East Yorkshire Solar Farm Limited | Drax 400kV Substation |  | 0 | 400 | 400 | 2029-09-30 | Scoping | Embedded | NGET | PV Array (Photo Voltaic/solar) | PRO-001759
a0l8e000000f6J0AAI | Drum of Clunas Wind and Solar Park | Plant Type: Energy Storage System;PV Array (Photo Voltaic/solar) -> Wind Onshore | CHANGED | BROADHAVEN DISTRIBUTION LIMITED | Drum of Clunas 275kV |  | 0 | 150 | 150 | 2031-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003970
a0l4L0000005imYQAQ | Dunlaw Extension | MW Increase / Decrease: 0.0 -> 126.25; Cumulative Total Capacity (MW): 29.75 MW -> 156.00 MW; MW Effective From: NULL -> 01/04/2032 | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Dunlaw Extension 132/33kV |  | 29.75 | 126.25 | 156 | 2032-04-01 | Built | Direct Connection | SPT | Wind Onshore | PRO-000061
a0l4L0000005ipGQAQ | Dunside Wind Farm (Formally Fallago Rig 2 Wind Farm) | Project Name: Fallago Rig 2 -> Dunside Wind Farm (Formally Fallago Rig 2 Wind Farm) | CHANGED | EDF ENERGY RENEWABLES LIMITED | Fallago 400/33kV |  | 0 | 100 | 100 | 2029-04-30 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | PRO-000526
a0l4L0000005imtQAA | Energy Isles | MW Effective From: 30/11/2028 -> 30/10/2032; Project Status: Awaiting Consents -> Consents Approved | CHANGED | ENERGY ISLES SHETLAND LIMITED | Energy Isles 132kV Substation |  | 0 | 120.3 | 120.3 | 2032-10-30 | Consents Approved | Direct Connection | SHET | Wind Onshore | PRO-000447
a0l4L0000005ibQQAQ | Euchanhead Wind Farm | MW Effective From: 29/10/2029 -> 29/10/2030 | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Euchanhead 132kV Substation |  | 0 | 112 | 112 | 2030-10-29 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001011
a0l8e000000f7klAAA | Fairburn Extension Wind Farm | Customer Name: SSE RENEWABLES SERVICES (UK) LIMITED -> SSE Renewables Services (UK) Limited | CHANGED | SSE Renewables Services (UK) Limited | Fairburn Extension 132/33kV Substation |  | 0 | 90 | 90 | 2031-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-004012
a0l8e0000012eoeAAA | Farr WindFarm | MW Effective From: 20/01/2030 -> 30/01/2030 | CHANGED | FARR WINDFARM LIMITED | Tomatin 275kV Substation |  | 0 | 144.8 | 144.8 | 2030-01-30 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-004381
a0l4L0000005izPQAQ | Fell Wind Farm | Connection Site: Fell Wind Farm 132/33kV Substation -> SPT Margree collector substation; MW Effective From: 31/10/2027 -> 31/10/2029 | CHANGED | ENERGYFARM UK FELL LLP | SPT Margree collector substation |  | 0 | 50 | 50 | 2029-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001755
a0l4L0000005izAQAQ | Fleet (Tertiary) | MW Effective From: 31/10/2025 -> 31/10/2026; Project Status: Scoping -> Consents Approved | CHANGED | CSE23 LIMITED | Fleet 400kV Substation |  | 0 | 47.5 | 47.5 | 2026-10-31 | Consents Approved | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-001087
a0l8e0000010wklAAA | Fleet Solar PV | MW Effective From: 13/12/2026 -> 07/08/2028; Plant Type: Energy Storage System;PV Array (Photo Voltaic/solar) -> PV Array (Photo Voltaic/solar) | CHANGED | FLEET SOLAR LIMITED | Fleet 400kV Substation |  | 0 | 57 | 57 | 2028-08-07 | Awaiting Consents | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-002814
a0l4L0000005iieQAA | Fron Goch | Connection Site: Pont Abraham GSP -> Pont Abraham 132KV | CHANGED | NANT MITHIL ENERGY PARK LIMITED | Pont Abraham 132KV |  | 0 | 252.7 | 252.7 | 2026-10-31 | Scoping | Embedded | NGET | Wind Onshore | PRO-001563
a0l4L0000005ihPQAQ | Gaerwen Wind Farm | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited | CHANGED | RWE Renewables UK Onshore Wind Limited | Gwyddelwern 400kV Substation |  | 0 | 67 | 67 | 2027-06-01 | Awaiting Consents | Direct Connection | NGET | Wind Onshore | PRO-001550
a0l8e000001Hr2cAAC | Galileo 05 | Customer Name: Galileo Empower UK Limited -> GALILEO 05 LIMITED | CHANGED | GALILEO 05 LIMITED | Lynemore Windfarm 132kV Substation |  | 0 | 84 | 84 | 2031-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-004173
a0l8e000000f40GAAQ | GALILEO 06 | Connection Site: Proposed Ferryside GSP -> Llandyfaelog 132kV Substation | CHANGED | Galileo Empower UK Limited | Llandyfaelog 132kV Substation |  | 0 | 175 | 175 | 2037-10-31 | Scoping | Embedded | NGET | Wind Onshore | PRO-003810
a0l4L0000005iXVQAY | Garbet Wind Farm | Customer Name: ENERGYFARM UK GARBET LLP -> GARBET WIND FARM LLP | CHANGED | GARBET WIND FARM LLP | Keith GSP |  | 0 | 46.2 | 46.2 | 2026-10-31 | Consents Approved | Embedded | SHET | Wind Onshore | PRO-001813
a0l4L0000005iWyQAI | Giants Burn Wind Farm | Customer Name: STATKRAFT UK LTD -> GB WIND FARM LIMITED | CHANGED | GB WIND FARM LIMITED | Dunoon GSP |  | 0 | 44 | 44 | 2030-05-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-002232
a0l4L0000005iQ5QAI | Gleann Eoghainn | Customer Name: RENANTIS UK LIMITED -> Renantis UK Limited; Connection Site: Edinbane 132/33kV Substation -> Dunvegan 132/33kV Grid Supply Point Substation; MW Effective From: 31/10/2027 -> 30/11/2029 | CHANGED | Renantis UK Limited | Dunvegan 132/33kV Grid Supply Point Substation |  | 0 | 25 | 25 | 2029-11-30 | Scoping | Embedded | SHET | Wind Onshore | PRO-001275
a0l4L0000005iyyQAA | Glendye Wind Farm | Stage: NULL -> 1.0; MW Increase / Decrease: 156.0 -> 124.8; Cumulative Total Capacity (MW): 156.00 MW -> 291.60 MW; Project Number: PRO-001389 -> PRO-001389-1 | CHANGED | GLENDYE WIND FARM LIMITED | Glendye Wind Farm Substation | 1 | 0 | 124.8 | 124.8 | 2028-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-001389-1
a0l4L0000005iyyQAA | Glendye Wind Farm | Stage: NULL -> 1.0; MW Increase / Decrease: 156.0 -> 124.8; Cumulative Total Capacity (MW): 156.00 MW -> 291.60 MW; Project Number: PRO-001389 -> PRO-001389-1 | CHANGED | GLENDYE WIND FARM LIMITED | Glendye Wind Farm Substation | 2 | 0 | 42 | 166.8 | 2034-04-30 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-001389-2
a0l4L0000005iwRQAQ | Glenmuckloch Wind Farm | MW Effective From: 29/09/2028 -> 31/05/2029 | CHANGED | GLENMUCKLOCH RENEWABLE ENERGY LIMITED | Glenmuckloch 132/33kV |  | 0 | 33.6 | 33.6 | 2029-05-31 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | PRO-000300
a0l4L0000005in1QAA | Glenshimmeroch Windfarm | MW Effective From: 31/10/2027 -> 31/10/2029 | CHANGED | ENERGYFARM UK GLENSHIMMEROCH LLP | SPT Margree collector substation |  | 0 | 45 | 45 | 2029-10-31 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000440
a0l8e00000120NhAAI | Glentarken Wind Farm | Customer Name: SSE RENEWABLES SERVICES (UK) LIMITED -> SSE Renewables Services (UK) Limited | CHANGED | SSE Renewables Services (UK) Limited | Killin GSP |  | 0 | 104 | 104 | 2031-11-30 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003627
a0l4L0000005ipOQAQ | Gordonbush Wind Farm | Customer Name: SSE GENERATION LIMITED -> SSE Generation Limited | CHANGED | SSE Generation Limited | Gordonbush GSP |  | 108 | 0 | 108 |  | Built | Direct Connection | SHET | Wind Onshore | PRO-000518
a0l4L0000005iRkQAI | Gordonstown Hill Wind Farm | Connection Site: Kintore GSP -> Rothienorman GSP | CHANGED | GORDONSTOWN HILL WIND FARM LIMITED | Rothienorman GSP |  | 12.5 | 0 | 12.5 |  | Built | Embedded | SHET | Wind Onshore | PRO-000936
a0l4L0000005iXfQAI | Greengairs East Wind Farm | MW Connected: 0.0 -> 42.64; MW Increase / Decrease: 42.64 -> 0.0; MW Effective From: 25/11/2022 -> NULL; Project Status: Awaiting Consents -> Built | CHANGED | GREENGAIRS EAST WIND FARM LIMITED | Cumbernauld 132/33kV |  | 42.64 | 0 | 42.64 |  | Built | Embedded | SPT | Wind Onshore | PRO-000880
a0l8e000000TPKNAA4 | Grimshader Wind Farm | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited | CHANGED | RWE Renewables UK Onshore Wind Limited | Grimshader Wind Farm Substation132 KV |  | 0 | 79.2 | 79.2 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003258
a0l4L0000005io5QAA | Hagshaw Hill Phase 1 | Connection Site: Coalburn 400/132kV -> Hagshaw Hill Wind Farm 33kV Substation; MW Connected: 0.0 -> 30.0; MW Increase / Decrease: 30.0 -> 0.0; MW Effective From: 30/05/2024 -> NULL; Project Status: Consents Approved -> Built | CHANGED | HAGSHAW HILL REPOWERING LTD | Hagshaw Hill Wind Farm 33kV Substation |  | 30 | 0 | 30 |  | Built | Direct Connection | SPT | Wind Onshore | PRO-000490
a0l4L0000005io6QAA | Hagshaw Hill Phase 2 | Connection Site: Coalburn 400/132kV -> Hagshaw Hill Wind Farm 33kV Substation; MW Connected: 0.0 -> 54.0; MW Increase / Decrease: 54.0 -> 0.0; MW Effective From: 30/05/2024 -> NULL; Project Status: Consents Approved -> Built | CHANGED | HAGSHAW HILL REPOWERING LTD | Hagshaw Hill Wind Farm 33kV Substation |  | 54 | 0 | 54 |  | Built | Direct Connection | SPT | Wind Onshore | PRO-000514
a0l4L0000005iysQAA | Hare Craig Wind Farm | Customer Name: ENERGYFARM UK HARE CRAIG LLP -> HARE CRAIG WINDFARM LLP | CHANGED | HARE CRAIG WINDFARM LLP | Hare Craig 33kV Substation |  | 0 | 46.2 | 46.2 | 2028-10-31 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | PRO-000940
a0l8e000000f6A6AAI | Hare Hill Repowering | MW Effective From: 31/10/2029 -> 31/10/2031 | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Hare Hill Repowering 132/33kV Substation |  | 0 | 114 | 114 | 2031-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-003963
a0l4L0000005ipdQAA | Hareshaw Rig Wind Farm | Customer Name: MUIRHALL ENERGY LIMITED -> HARESHAW RIG WF LIMITED; MW Effective From: 30/11/2026 -> 31/10/2029 | CHANGED | HARESHAW RIG WF LIMITED | Hopsrig Collector 132/33kV Substation |  | 0 | 40 | 40 | 2029-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000543
a0l4L0000005icnQAA | Harestanes West Wind Farm | Project Name: Old Forest of Ae -> Harestanes West Wind Farm; Connection Site: Old Forest of Ae 33kV Substation -> Harestanes West Wind Farm 132/33kV; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 56.00 MW -> 137.00 MW; MW Effective From: 31/10/2027 -> 01/09/2029; Project Number: PRO-001075 -> PRO-001075-1 | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Harestanes West Wind Farm 132/33kV | 1 | 0 | 56 | 56 | 2029-09-01 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001075-1
a0l4L0000005icnQAA | Harestanes West Wind Farm | Project Name: Old Forest of Ae -> Harestanes West Wind Farm; Connection Site: Old Forest of Ae 33kV Substation -> Harestanes West Wind Farm 132/33kV; Stage: NULL -> 1.0; Cumulative Total Capacity (MW): 56.00 MW -> 137.00 MW; MW Effective From: 31/10/2027 -> 01/09/2029; Project Number: PRO-001075 -> PRO-001075-1 | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Harestanes West Wind Farm 132/33kV | 2 | 0 | 25 | 81 | 2035-07-01 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001075-2
a0l8e000000TPKIAA4 | Heastabhal Wind Farm | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited | CHANGED | RWE Renewables UK Onshore Wind Limited | Heastabhal Wind Farm Substation 132 KV |  | 0 | 66 | 66 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003257
a0l4L0000005imKQAQ | High Constellation Windfarm | Connection Site: Crossaig 132kV Substation -> High Constellation 132/33kV Substation; MW Effective From: 30/04/2025 -> 31/07/2027 | CHANGED | HIGH CONSTELLATION WINDFARM LIMITED | High Constellation 132/33kV Substation |  | 0 | 50 | 50 | 2027-07-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-000416
a0l4L0000005iRiQAI | Hill of Towie 2 Wind Farm | Customer Name: Renewable Energy Systems Limited -> GREENHILLS 1 LIMITED | CHANGED | GREENHILLS 1 LIMITED | Keith GSP |  | 0 | 36 | 36 | 2030-06-01 | Consents Approved | Embedded | SHET | Wind Onshore | PRO-000938
a0l4L0000005ibYQAQ | Hollandmey Renewable Energy Development | MW Effective From: 01/05/2029 -> 31/05/2030; Project Status: Scoping -> Consents Approved | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Hollandmey Renewable Energy Development132/33kV Substation |  | 0 | 49.5 | 49.5 | 2030-05-31 | Consents Approved | Direct Connection | SHET | Wind Onshore | PRO-001094
a0l4L0000005isfQAA | Hopsrig Wind Farm | MW Effective From: 30/11/2026 -> 31/10/2027 | CHANGED | HOPSRIG WIND FARM LIMITED | Hopsrig Collector 132/33kV Substation |  | 0 | 48 | 48 | 2027-10-31 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000318
a0l4L0000005isgQAA | Kennoxhead Wind Farm | MW Effective From: 01/04/2028 -> 28/04/2028 | CHANGED | ORSTED ONSHORE UK LIMITED | Kennoxhead GSP |  | 0 | 112 | 112 | 2028-04-28 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000319
a0l8e000000f6hCAAQ | Kilbraur North Wind Farm | Gate: -> 1.0 | CHANGED | EDF ENERGY RENEWABLES LIMITED | Kilbraur Wind Farm Substation |  | 0 | 79.2 | 79.2 | 2031-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003987 | 1
a0l4L0000005imcQAA | Kilgallioch Wind Farm | Project Name: Kilgallioch Wind Farm and Kilgallioch Wind Farm Extension - Turbines -> Kilgallioch Wind Farm | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Kilgallioch 275kV Substation | 1 | 228 | 0 | 228 |  | Built | Direct Connection | SPT | Wind Onshore | PRO-000065-1
a0l4L0000005imcQAA | Kilgallioch Wind Farm | Project Name: Kilgallioch Wind Farm and Kilgallioch Wind Farm Extension - Turbines -> Kilgallioch Wind Farm | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Kilgallioch 275kV Substation | 2 | 0 | 46 | 274 | 2025-04-08 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000065-2
a0l4L0000005ikKQAQ | Knockcronal Wind Farm | MW Effective From: 30/10/2028 -> 30/10/2029; Project Status: Scoping -> Awaiting Consents | CHANGED | Knockcronal Wind Farm Limited | Knockcronal Wind Farm 33kV Substation |  | 0 | 59.4 | 59.4 | 2029-10-30 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | PRO-001801
a0l4L0000005inYQAQ | Knockodhar Wind Farm | Connection Site: Mark Hill 275/132kV -> Knockodhar Wind Farm 132kV Substation | CHANGED | REG KNOCKODHAR LIMITED | Knockodhar Wind Farm 132kV Substation |  | 0 | 120 | 120 | 2028-04-30 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000483
a0l8e0000011yY5AAI | Knockton Wind Farm | Connection Site: Knockton Wind Farm 132kV Substation -> Alyth 400kV Substation | CHANGED | ORSTED ONSHORE UK LIMITED | Alyth 400kV Substation |  | 0 | 130.2 | 130.2 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-003524
a0l4L0000005ivMQAQ | Lethen Wind Farm | MW Effective From: 31/10/2029 -> 31/12/2033; Plant Type: Energy Storage System;Wind Onshore -> Wind Onshore | CHANGED | FRED. OLSEN RENEWABLES LIMITED | Lethen Wind Farm 132/33kV Substation |  | 0 | 114 | 114 | 2033-12-31 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-002307
a0l4L0000005idSQAQ | Loch Liath Wind Farm | Project Status: Scoping -> Awaiting Consents | CHANGED | LOCH LIATH WIND FARM LIMITED | Loch Liath 132/33kV Substation |  | 0 | 99 | 99 | 2035-10-31 | Awaiting Consents | Direct Connection | SHET | Wind Onshore | PRO-001671
a0l4L0000005isNQAQ | Loganhead Windfarm | MW Effective From: 31/10/2026 -> 31/10/2027 | CHANGED | LOGANHEAD WF LIMITED | Hopsrig Collector 132/33kV Substation |  | 0 | 36 | 36 | 2027-10-31 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | PRO-000306
a0l4L0000005iynQAA | Lorg Extension Wind Farm | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited; Connection Site: Lorg Wind Farm 132/32kV -> Lorg Extension Wind Farm 132/33kV Substation | CHANGED | RWE Renewables UK Onshore Wind Limited | Lorg Extension Wind Farm 132/33kV Substation |  | 0 | 33 | 33 | 2029-08-13 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-002430
a0l4L0000005ikXQAQ | Lorg Wind Farm | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited; MW Effective From: 30/04/2027 -> 07/04/2027 | CHANGED | RWE Renewables UK Onshore Wind Limited | Lorg Wind Farm 132/32kV |  | 0 | 69.5 | 69.5 | 2027-04-07 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000153
a0l4L0000005ij9QAA | Margree Wind Farm | Connection Site: Quantans Hill 132kV -> SPT Margree collector substation; MW Effective From: 31/10/2027 -> 31/10/2029 | CHANGED | ENERGYFARM UK MARGREE LLP | SPT Margree collector substation |  | 0 | 50 | 50 | 2029-10-31 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | PRO-001789
a0l8e0000010wfMAAQ | Merthyr Solar and Battery | Cumulative Total Capacity (MW): 330.00 MW -> 285.00 MW | CHANGED | E.E.W. ECO ENERGY WORLD DEVELOPMENT HOLDING LIMITED | Cilfynydd 400kV Substation | 1 | 0 | 110 | 110 | 2029-05-12 | Scoping | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-002757-1
a0l8e0000010wfMAAQ | Merthyr Solar and Battery | Cumulative Total Capacity (MW): 330.00 MW -> 285.00 MW | CHANGED | E.E.W. ECO ENERGY WORLD DEVELOPMENT HOLDING LIMITED | Cilfynydd 400kV Substation | 2 | 0 | 65 | 175 | 2037-10-31 | Scoping | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-002757-2
a0l4L0000005ifqQAA | Mwdwl Eithin Energy Park | MW Effective From: 31/10/2026 -> 30/06/2030 | CHANGED | MOEL CHWA ENERGY PARK LIMITED | Gwyddelwern 400kV Substation |  | 0 | 81.2 | 81.2 | 2030-06-30 | Scoping | Direct Connection | NGET | Wind Onshore | PRO-001511
a0l4L0000005iNcQAI | Nant Aman | MW Effective From: 01/10/2028 -> 13/12/2030 | CHANGED | NANT AMAN ENERGY PARK LIMITED | Rhigos 400kV Substation |  | 0 | 143 | 143 | 2030-12-13 | Scoping | Direct Connection | NGET | Wind Onshore | PRO-001640
a0l4L0000005iSHQAY | Narachan Wind Farm | MW Effective From: 30/11/2028 -> 30/04/2030 | CHANGED | ENERGYFARM UK NARACHAN LLP | Carradale 1 GSP |  | 0 | 72.6 | 72.6 | 2030-04-30 | Scoping | Embedded | SHET | Wind Onshore | PRO-001926
a0l4L0000005it0QAA | North Lowther Energy Initiative | Connection Site: NLEI GSP -> NLEI Windfarm 132/33kV substation; MW Effective From: 01/04/2028 -> 30/04/2031 | CHANGED | NLEI LTD | NLEI Windfarm 132/33kV substation |  | 0 | 151.2 | 151.2 | 2031-04-30 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000344
a0l4L0000005iXmQAI | Norton Solar Farm | Customer Name: JBM SOLAR PROJECTS 29 LIMITED -> RWE Renewables UK Solar and Storage Limited | CHANGED | RWE Renewables UK Solar and Storage Limited | Norton GSP |  | 0 | 180 | 180 | 2031-10-31 | Scoping | Embedded | NGET | PV Array (Photo Voltaic/solar) | PRO-001875
a0l8e0000010wVjAAI | Olivers Forest Wind Farm | Project Status: Scoping -> Awaiting Consents | CHANGED | Oliver Forest Wind Farm Limited | Olivers Forest Wind Farm 132kV Substation |  | 0 | 79.2 | 79.2 | 2031-04-30 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | PRO-002648
a0l4L0000005inwQAA | Overhill Wind Farm | Connection Site: Overhill WF 132kV Substation -> Overhill 132kV Substation; MW Effective From: 30/06/2027 -> 06/06/2029 | CHANGED | ENERGYFARM UK OVERHILL LLP | Overhill 132kV Substation |  | 0 | 50 | 50 | 2029-06-06 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000472
a0l8e0000010wm8AAA | Penninghame Wind Farm | Gate: -> 1.0 | CHANGED | EDF ENERGY RENEWABLES LIMITED | Penninghame Substation |  | 0 | 60 | 60 | 2031-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-002830 | 1
a0l8e0000010wbAAAQ | Philiphaugh Wind Farm | Gate: -> 1.0 | CHANGED | EDF ENERGY RENEWABLES LIMITED | Philipaugh Substation |  | 0 | 175 | 175 | 2033-05-30 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-002708 | 1
a0l4L0000005imsQAA | Priestgill Wind Farm | Connection Site: Elvanfoot 275/132/33kV -> Elvanfoot 400/275/33kV; MW Effective From: 06/12/2024 -> 30/11/2026 | CHANGED | PRIESTGILL WIND FARM LIMITED | Elvanfoot 400/275/33kV |  | 0 | 43.63 | 43.63 | 2026-11-30 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000448
a0l4L0000005iOeQAI | Quantans Hill Wind Farm | MW Effective From: 30/04/2027 -> 02/07/2029 | CHANGED | VATTENFALL WIND POWER LTD | Quantans Hill 132kV Substation |  | 0 | 95 | 95 | 2029-07-02 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001247
a0l8e000000f6yfAAA | RAF Newton PV solar | MW Effective From: 31/10/2032 -> 30/10/2034 | CHANGED | Bluestone Energy Ltd | Stoke Bardolph GSP |  | 0 | 149.7 | 149.7 | 2034-10-30 | Scoping | Embedded | NGET | PV Array (Photo Voltaic/solar) | PRO-003995
a0l8e000001HrZ3AAK | RIGG HOUSE PV FARM | Customer Name: Firma Vogt Solar Ltd -> FVS DEAN MOOR LIMITED | CHANGED | FVS DEAN MOOR LIMITED | Harker GSP |  | 0 | 150 | 150 | 2037-10-31 | Scoping | Embedded | NGET | PV Array (Photo Voltaic/solar) | PRO-004209
a0l4L0000005it6QAA | Sanquhar II Wind Farm | Connection Site: Sanquhar 132/33kV -> Glenglass 132kV Substation; Stage: NULL -> 1.0; MW Increase / Decrease: 250.0 -> 137.0; Cumulative Total Capacity (MW): 250.00 MW -> 387.00 MW; MW Effective From: 30/04/2024 -> 31/07/2026; Project Number: PRO-000352 -> PRO-000352-1 | CHANGED | SANQUHAR II COMMUNITY WIND CO LTD | Glenglass 132kV Substation | 1 | 0 | 137 | 137 | 2026-07-31 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000352-1
a0l4L0000005it6QAA | Sanquhar II Wind Farm | Connection Site: Sanquhar 132/33kV -> Glenglass 132kV Substation; Stage: NULL -> 1.0; MW Increase / Decrease: 250.0 -> 137.0; Cumulative Total Capacity (MW): 250.00 MW -> 387.00 MW; MW Effective From: 30/04/2024 -> 31/07/2026; Project Number: PRO-000352 -> PRO-000352-1 | CHANGED | SANQUHAR II COMMUNITY WIND CO LTD | Glenglass 132kV Substation | 2 | 0 | 113 | 250 | 2027-02-28 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000352-2
a0l4L0000005ismQAA | Scoop Hill Wind Farm | Customer Name: CWP Energy Limited -> Community Windpower Limited | CHANGED | Community Windpower Limited | Scoop Hill Wind Farm 132kV Substation |  | 0 | 500 | 500 | 2027-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000327
a0l4L0000005icwQAA | Sheirdrim Wind Farm | MW Effective From: 31/10/2029 -> 01/04/2032 | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Sheirdrim 132kV Substation |  | 0 | 84 | 84 | 2032-04-01 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-001066
a0l4L0000005inqQAA | Stranoch Wind Farm | MW Effective From: 29/08/2025 -> 09/10/2026 | CHANGED | Stranoch Windfarm Limited | Stranoch Wind 132/33kV Substation |  | 0 | 102 | 102 | 2026-10-09 | Consents Approved | Direct Connection | SPT | Wind Onshore | PRO-000127
a0l4L0000005iXpQAI | Strath Tirry | Stage: 1.0 -> NULL; MW Increase / Decrease: 20.0 -> 34.8; Cumulative Total Capacity (MW): 54.80 MW -> 34.80 MW; MW Effective From: 31/10/2025 -> 19/12/2029; Plant Type: Energy Storage System;Wind Onshore -> Wind Onshore; Project Number: PRO-001363-1 -> PRO-001363 | CHANGED | Strath Tirry Wind Energy 2021 Ltd | Lairg GSP |  | 0 | 34.8 | 34.8 | 2029-12-19 | Scoping | Embedded | SHET | Wind Onshore | PRO-001363
a0l4L0000005iUPQAY | Strathrory Wind Farm | Customer Name: ENERGYFARM UK STRATHRORY LLP -> STRATHRORY WIND FARM LLP | CHANGED | STRATHRORY WIND FARM LLP | Alness GSP |  | 0 | 36 | 36 | 2024-03-31 | Consents Approved | Embedded | SHET | Wind Onshore | PRO-001812
a0l4L0000005ix6QAA | Strathy South Wind | Customer Name: SSE GENERATION LIMITED -> SSE Generation Limited | CHANGED | SSE Generation Limited | Strathy South 132/33kV Substation |  | 0 | 207.6 | 207.6 | 2027-04-25 | Scoping | Direct Connection | SHET | Wind Onshore | PRO-000183
a0l4L0000005ionQAA | Strathy Wood | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited | CHANGED | RWE Renewables UK Onshore Wind Limited | Strathy Wood 132/33kV Substation | 1 | 0 | 54.4 | 54.4 | 2026-09-30 | Consents Approved | Direct Connection | SHET | Wind Onshore | PRO-000154-1
a0l4L0000005ionQAA | Strathy Wood | Customer Name: RWE RENEWABLES UK ONSHORE WIND LIMITED -> RWE Renewables UK Onshore Wind Limited | CHANGED | RWE Renewables UK Onshore Wind Limited | Strathy Wood 132/33kV Substation | 2 | 0 | 9.1 | 63.5 | 2026-09-30 | Consents Approved | Direct Connection | SHET | Wind Onshore | PRO-000154-2
a0l4L0000005iXOQAY | Sulgrave Solar PV | Connection Site: East Claydon GSP (SEPD) -> East Claydon GSP (NGED EM) | CHANGED | EDF ENERGY RENEWABLES LIMITED | East Claydon GSP (NGED EM) |  | 0 | 129.8 | 129.8 | 2026-10-30 | Scoping | Embedded | NGET | PV Array (Photo Voltaic/solar) | PRO-001572
a0l8e0000010wgPAAQ | Sundhope Wind Farm | Customer Name: Sundhope Energy Limited -> Black Knowe Energy Limited | CHANGED | Black Knowe Energy Limited | Sundhope 132kV Substation |  | 0 | 180 | 180 | 2033-05-30 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-002767
a0l4L0000005ifXQAQ | Sundon Pivoted Power | Plant Type: Energy Storage System -> PV Array (Photo Voltaic/solar) | CHANGED | PIVOTED POWER LLP | Sundon 400kV Substation |  | 49.9 | 0 | 49.9 |  | Built | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-001123
a0l4L0000005iNdQAI | Tarenni | MW Effective From: 01/10/2028 -> 31/12/2030 | CHANGED | TARENNI ENERGY PARK LIMITED | Rhigos 400kV Substation |  | 0 | 188 | 188 | 2030-12-31 | Scoping | Direct Connection | NGET | Wind Onshore | PRO-001641
a0l4L0000005iffQAA | Troston Wind Farm | Connection Site: Troston Wind Farm 132kV Substation -> Margree 132kV Collector Substation; MW Effective From: 31/10/2027 -> 31/10/2029 | CHANGED | TROSTON WINDFARM LIMITED | Margree 132kV Collector Substation |  | 0 | 68 | 68 | 2029-10-31 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | PRO-001115
a0l4L0000005izFQAQ | Twyn Hywel Cillfynydd | MW Increase / Decrease: 160.0 -> 107.8; Cumulative Total Capacity (MW): 160.00 MW -> 107.80 MW; MW Effective From: 31/03/2026 -> 01/04/2027 | CHANGED | Twyn Hywel Energy Park Ltd | Cilfynydd 400kV Substation |  | 0 | 107.8 | 107.8 | 2027-04-01 | Scoping | Direct Connection | NGET | Wind Onshore | PRO-001497
a0l8e000001HoGMAA0 | Upper Beoch Windfarm | Connection Site: New Cumnock 275/132kV Substation -> New Cumnock North 132kV Substation | CHANGED | BROCKWELL ENERGY LIMITED | New Cumnock North 132kV Substation |  | 0 | 80 | 80 | 2033-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-004068
a0l4L0000005isvQAA | Viking Wind Farm | MW Connected: 0.0 -> 443.0; MW Increase / Decrease: 443.0 -> 0.0; MW Effective From: 01/07/2024 -> NULL; Project Status: Consents Approved -> Built | CHANGED | VIKING ENERGY WIND FARM LLP | Kergord GSP |  | 443 | 0 | 443 |  | Built | Direct Connection | SHET | Wind Onshore | PRO-000338
a0l8e0000010wPRAAY | West Andershaw Wind Farm | Gate: -> 1.0 | CHANGED | WEST ANDERSHAW WIND FARM LIMITED | West Andershaw 132kV Substation |  | 0 | 85.8 | 85.8 | 2030-04-30 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-002584 | 1
a0l8e0000012gbeAAA | West Grimsby Farm | Customer Name: ELGIN ENERGY ES CO LIMITED -> Elgin Energy Holdings Limited | CHANGED | Elgin Energy Holdings Limited | Grimsby West GSP |  | 0 | 150 | 150 | 2035-10-31 | Awaiting Consents | Embedded | NGET | PV Array (Photo Voltaic/solar) | PRO-004434
a0l4L0000005iT2QAI | West Torrisdale | MW Effective From: 30/04/2027 -> 31/05/2028 | CHANGED | ESB ASSET DEVELOPMENT UK LIMITED | Carradale 1 GSP |  | 0 | 50 | 50 | 2028-05-31 | Scoping | Embedded | SHET | Wind Onshore | PRO-000944
a0l4L0000005ig2QAA | Wether Hill | MW Effective From: 01/12/2028 -> 29/09/2031 | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Wether Hill 132/33KV Substation |  | 0 | 66 | 66 | 2031-09-29 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-001527
a0l4L0000005imeQAA | Whitelee | Cumulative Total Capacity (MW): 965.00 MW -> 2,138.00 MW; MW Effective From: 15/06/2029 -> 02/05/2031; Plant Type: Energy Storage System;Wind Onshore -> Wind Onshore | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Whitelee 275/33kV | 1 | 305 | 0 | 305 |  | Built | Direct Connection | SPT | Wind Onshore | PRO-000067-1
a0l4L0000005imeQAA | Whitelee | Cumulative Total Capacity (MW): 965.00 MW -> 2,138.00 MW; MW Effective From: 15/06/2029 -> 02/05/2031; Plant Type: Energy Storage System;Wind Onshore -> Wind Onshore | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Whitelee 275/33kV | 2 | 0 | 50 | 355 | 2031-05-02 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000067-2
a0l4L0000005imeQAA | Whitelee | Cumulative Total Capacity (MW): 965.00 MW -> 2,138.00 MW; MW Effective From: 15/06/2029 -> 02/05/2031; Plant Type: Energy Storage System;Wind Onshore -> Wind Onshore | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Whitelee 275/33kV | 3 | 0 | 305 | 660 | 2033-04-25 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000067-3
a0l4L0000005imeQAA | Whitelee | Cumulative Total Capacity (MW): 965.00 MW -> 2,138.00 MW; MW Effective From: 15/06/2029 -> 02/05/2031; Plant Type: Energy Storage System;Wind Onshore -> Wind Onshore | CHANGED | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Whitelee 275/33kV | 4 | 0 | 158 | 818 | 2034-04-27 | Scoping | Direct Connection | SPT | Wind Onshore | PRO-000067-4
a0l4L0000005iqjQAA | Windy Standard II (Brockloch Rig) Wind Farm | Stage: 1.0 -> NULL; Cumulative Total Capacity (MW): 136.50 MW -> 61.50 MW; MW Effective From: 30/06/2024 -> NULL; Project Number: PRO-000233-1 -> PRO-000233 | CHANGED | BROCKLOCH RIG WINDFARM LIMITED | Dun Hill 132/33kV |  | 61.5 | 0 | 61.5 |  | Built | Direct Connection | SPT | Wind Onshore | PRO-000233
a0l8e0000010x0FAAQ | Woburn Solar Farm | Gate: -> 1.0 | CHANGED | SolarThree Ltd | Dunstable 400kV Substation |  | 0 | 840 | 840 | 2031-10-31 | Scoping | Direct Connection | NGET | PV Array (Photo Voltaic/solar) | PRO-003033 | 1