## Pot 3
Change Type | Count
New Entries | 0
Deleted Entries | 0
Modified Entries | 0
Detailed Change Records:

## Pot 1
Change Type | Count
New Entries | 3
Deleted Entries | 4
Modified Entries | 5
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
NEW | New entry in TEC register. | Chirmorie Wind Farm | CHIRMORIE WIND FARM LIMITED | Chirmorie Wind Farm substation |  | 0.0 | 91.0 | 91.0 | 2027-04-30 | Consents Approved | Direct Connection | SPT | Wind Onshore | a0l4L0000005inCQAQ | PRO-000094 | 2
NEW | New entry in TEC register. | Clashindarroch 2 | VATTENFALL WIND POWER LTD | Cairnford GSP |  | 0.0 | 63.0 | 63.0 | 2027-06-04 | Scoping | Embedded | SHET | Wind Onshore | a0l4L0000005iV1QAI | PRO-000041 | 2
NEW | New entry in TEC register. | Garbet Wind Farm | GARBET WIND FARM LLP | Keith 2 132/33kV GSP Substation |  | 0.0 | 46.2 | 46.2 | 2026-10-31 | Consents Approved | Embedded | SHET | Wind Onshore | a0l4L0000005iXVQAY | PRO-001813 | 2
DELETED | Entry removed from TEC register. | Ackron Wind Farm | ACKRON WIND FARM LTD | Dounreay GSP |  | 0.0 | 49.9 | 49.9 | 2028-08-31 | Scoping | Embedded | SHET | Wind Onshore | a0l4L0000005iTjQAI | PRO-001446
DELETED | Entry removed from TEC register. | Chirmorie Wind Farm | CHIRMORIE WIND FARM LIMITED | Chirmorie Wind Farm substation | 1.0 | 0.0 | 91.0 | 91.0 | 2027-04-30 | Consents Approved | Direct Connection | SPT | Wind Onshore | a0l4L0000005inCQAQ | PRO-000094-1 | 2
DELETED | Entry removed from TEC register. | Clashindarroch 2 | VATTENFALL WIND POWER LTD | Cairnford GSP | 1.0 | 0.0 | 63.0 | 63.0 | 2027-06-04 | Scoping | Embedded | SHET | Wind Onshore | a0l4L0000005iV1QAI | PRO-000041-1 | 2
DELETED | Entry removed from TEC register. | Garbet Wind Farm | GARBET WIND FARM LLP | Keith 2 132/33kV GSP Substation | 1.0 | 0.0 | 46.2 | 46.2 | 2026-10-31 | Consents Approved | Embedded | SHET | Wind Onshore | a0l4L0000005iXVQAY | PRO-001813-1 | 2
MODIFIED | Connection Date: '2027-07-31' -> '2028-09-10'; Gate Status: '' -> '2' | Chleansaid Wind Farm | ESB ASSET DEVELOPMENT UK LIMITED | Chleansaid Wind Farm 132kV Substation |  | 0.0 | 96.0 | 96.0 | 2028-09-10 | Scoping | Direct Connection | SHET | Wind Onshore | a0l4L0000005iY6QAI | PRO-001608 | 2
MODIFIED | Connection Date: '2027-07-31' -> '2028-10-31'; Gate Status: '' -> '2' | High Constellation Windfarm | HIGH CONSTELLATION WINDFARM LIMITED | High Constellation 132/33kV Substation |  | 0.0 | 50.0 | 50.0 | 2028-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0l4L0000005imKQAQ | PRO-000416 | 2
MODIFIED | Capacity: '0.0' -> '450.0'; Connection Date: '' -> '2033-10-31' | JG Pears | JG PEARS GRID CONNECTION LIMITED | High Marnham 275kV Substation |  | 30.0 | 420.0 | 450.0 | 2033-10-31 | Built | Direct Connection | NGET | CHP (Combined Heat and Power);Energy Storage System;PV Array (Photo Voltaic/solar);Wind Onshore | a0l4L0000005irEQAQ | PRO-000250
MODIFIED | Gate Status: '' -> '1' | Norwich Main BESS | TASWAY ENERGY PARK LIMITED | North Anglia Connection Node A 400kV | 2.0 | 0.0 | 700.0 | 949.9 | 2034-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000f4xHAAQ | PRO-003894-2 | 1
MODIFIED | Gate Status: '' -> '1' | Rat Hall Mod App | Kingsway Solar Farm Limited | South Anglia Connection Node C 400kV Substation | 1.0 | 0.0 | 200.0 | 200.0 | 2032-10-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000f41YAAQ | PRO-003824-1 | 1