## Pot 3
Change Type | Count
New Entries | 0
Deleted Entries | 0
Modified Entries | 0
Detailed Change Records:

## Pot 1
Change Type | Count
New Entries | 0
Deleted Entries | 0
Modified Entries | 49
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
MODIFIED | Gate Status: '' -> '1' | Aberarder Extension Wind Farm | Renewable Energy Systems Limited | Aberarder Extension Wind Farm 132/33kV Substation |  | 0.0 | 138.0 | 138.0 | 2031-04-30 | Scoping | Direct Connection | SHET | Energy Storage System;Wind Onshore | a0l8e0000010wQ0AAI | PRO-002589 | 1
MODIFIED | Gate Status: '' -> '1' | Abhainn Dubh Wind Farm | E Power Limited | Abhainn Dubh Wind Farm 132kV Substation |  | 0.0 | 75.0 | 75.0 | 2029-05-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0l4L0000005ivFQAQ | PRO-002272 | 1
MODIFIED | Gate Status: '' -> '1' | Aultmore Wind Farm (2023) | VATTENFALL WIND POWER LTD | Aultmore Wind Farm 132/33kV Substation |  | 0.0 | 105.0 | 105.0 | 2030-09-30 | Scoping | Direct Connection | SHET | Energy Storage System;Wind Onshore | a0l8e000000f6JjAAI | PRO-003975 | 1
MODIFIED | Gate Status: '' -> '1' | Ballygroggan Wind Farm | DALRIADA RENEWABLES LIMITED | Tangy IV 132KV Substation |  | 0.0 | 96.0 | 96.0 | 2034-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0l8e000000exU0AAI | PRO-003733 | 1
MODIFIED | Gate Status: '' -> '1' | Beinn Tharsuinn Repower | SCOTTISHPOWER RENEWABLES (UK) LIMITED | BEINN THURSUNN REPOWER 275/33KV |  | 0.0 | 84.0 | 84.0 | 2029-10-31 | Scoping | Direct Connection | NGET | Wind Onshore | a0l4L0000005iaNQAQ | PRO-001035 | 1
MODIFIED | Gate Status: '' -> '1' | Bicker Fen | IB VOGT UK LTD | Trent Valley South Connection Node C 400kV Substation |  | 0.0 | 400.0 | 400.0 | 2034-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000001HxlxAAC | PRO-004295 | 1
MODIFIED | Gate Status: '' -> '1' | Bolney Farm 2 | DRAGON GREEN 7 RENEWABLES LTD | DRAGON GREEN 400kV SUBSTATION |  | 0.0 | 700.0 | 700.0 | 2037-11-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000010wdQAAQ | PRO-002733 | 1
MODIFIED | Gate Status: '' -> '1' | Borders Wind Farm | EDF ENERGY RENEWABLES LIMITED | Borders Windfarm 132kV |  | 0.0 | 400.0 | 400.0 | 2033-05-30 | Scoping | Direct Connection | SPT | Wind Onshore | a0l4L0000005iZKQAY | PRO-001977 | 1
MODIFIED | Gate Status: '' -> '1' | Bramley Farm | BRAMLEY 2 RENEWABLES LTD | Basingstoke East 400kV Substation |  | 0.0 | 200.0 | 200.0 | 2038-03-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000010wYJAAY | PRO-002675 | 1
MODIFIED | Gate Status: '' -> '1' | Bramley Farm 2 | BRAMLEY 7 RENEWABLES LTD | Basingstoke East 400kV Substation |  | 0.0 | 700.0 | 700.0 | 2038-05-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000010wdaAAA | PRO-002735 | 1
MODIFIED | Gate Status: '' -> '1' | Butlers Energy Project | IG RENEWABLES SPV 1 LTD | South Anglia Connection Node B 400kV Substation |  | 0.0 | 480.0 | 480.0 | 2034-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000f64WAAQ | PRO-003946 | 1
MODIFIED | Gate Status: '' -> '1' | Chapel Rush Solar | RWE Renewables UK Solar and Storage Limited | North Humber Connection Node A 400kV Substation |  | 0.0 | 600.0 | 600.0 | 2035-10-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012hpXAAQ | PRO-004538 | 1
MODIFIED | Gate Status: '' -> '1' | Chesterfield | SSE RENEWABLES SOLAR & BATTERY HOLDINGS LIMITED | Chesterfield 400kV Substation (Not yet constructed) |  | 0.0 | 600.0 | 600.0 | 2032-10-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000f4iJAAQ | PRO-003861 | 1
MODIFIED | Gate Status: '' -> '1' | Clean Planet Solar | Clean Planet Solar Farm Limited | Frodsham 400kV Substation |  | 0.0 | 500.0 | 500.0 | 2037-11-01 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar);Reactive Compensation | a0l8e0000011yXgAAI | PRO-003519 | 1
MODIFIED | Gate Status: '' -> '1' | Correen Hills Wind Farm | EDF ENERGY RENEWABLES LIMITED | Correen Hills Wind Farm 132kV Substation |  | 0.0 | 68.4 | 68.4 | 2031-09-30 | Scoping | Direct Connection | SHET | Wind Onshore | a0l4L0000005iNoQAI | PRO-001825 | 1
MODIFIED | Gate Status: '' -> '1' | Coryton | Coryton 10 Renewables Limited | South Anglia Connection Node C 400kV Substation |  | 0.0 | 1000.0 | 1000.0 | 2034-10-31 | Scoping | Direct Connection | NGET | Demand;PV Array (Photo Voltaic/solar) | a0l8e000000TPQlAAO | PRO-003407 | 1
MODIFIED | Gate Status: '' -> '1' | Craiginmoddie Wind Farm | ENERGYFARM UK CRAIGINMODDIE LLP | Maybole 132/33kV |  | 0.0 | 92.4 | 92.4 | 2031-09-30 | Scoping | Direct Connection | SPT | Wind Onshore | a0l8e000000f41xAAA | PRO-003829 | 1
MODIFIED | Gate Status: '' -> '1' | Dorenell Battery | CLASHINDARROCH WINDFARM EXTENSION LIMITED | Dorenell BESS 132KV substation |  | 0.0 | 37.5 | 37.5 | 2023-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0l4L0000005ilvQAA | PRO-000427 | 1
MODIFIED | Gate Status: '' -> '1' | Drakelow PV & BESS Station | IBV Elford Park Solar Limited | Drakelow 400kV Substation |  | 0.0 | 400.0 | 400.0 | 2037-10-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000TPHnAAO | PRO-003238 | 1
MODIFIED | Gate Status: '' -> '1' | Epworth PV & BESS Station | IBV KELFIELD SOLAR LTD | Trent Valley North Connection Node B 400kV Substation |  | 0.0 | 150.0 | 150.0 | 2037-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000ew2TAAQ | PRO-003644 | 1
MODIFIED | Gate Status: '' -> '1' | ER BRF 2 Energy | ER PROJECT DEVELOPMENT CO LIMITED | Bramford 400kV Substation |  | 0.0 | 249.0 | 249.0 | 2033-07-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000exSYAAY | PRO-003725 | 1
MODIFIED | Gate Status: '' -> '1' | Farr WindFarm | FARR WINDFARM LIMITED | FARR WIND FARM 132/33KV SUBSTATION |  | 0.0 | 144.8 | 144.8 | 2030-01-30 | Scoping | Direct Connection | SHET | Wind Onshore | a0l8e0000012eoeAAA | PRO-004381 | 1
MODIFIED | Gate Status: '' -> '1' | Forsinain Wind Farm | Forsinain Forest Wind Farm Limited | Connagill 132kV Substation |  | 0.0 | 99.0 | 99.0 | 2037-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0lJ9000000POkIIAW | PRO-006123 | 1
MODIFIED | Gate Status: '' -> '1' | Fleet Farm | BASINGSTOKE EAST 2 RENEWABLES LTD | Basingstoke East 400kV Substation |  | 0.0 | 200.0 | 200.0 | 2038-04-30 | Scoping | Direct Connection | NGET | Demand;Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000010wYYAAY | PRO-002678 | 1
MODIFIED | Gate Status: '' -> '1' | Fleet Farm 2 | Basingstoke East 7 Renewables Ltd | Basingstoke East 400kV Substation |  | 0.0 | 700.0 | 700.0 | 2038-06-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000010wduAAA | PRO-002739 | 1
MODIFIED | Gate Status: '' -> '1' | Glentarken Wind Farm | SSE Renewables Services (UK) Limited | GLENTARKEN WIND FARM 132/33KV SUBSTATION |  | 0.0 | 104.0 | 104.0 | 2031-11-30 | Scoping | Direct Connection | SHET | Wind Onshore | a0l8e00000120NhAAI | PRO-003627 | 1
MODIFIED | Gate Status: '' -> '1' | Greengage Farm | Renewable Energy Systems Limited | Biggleswade 400kV Substation |  | 0.0 | 500.0 | 500.0 | 2034-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012jPcAAI | PRO-004675 | 1
MODIFIED | Gate Status: '' -> '1' | Grimshader Wind Farm | RWE Renewables UK Onshore Wind Limited | Grimshader Wind Farm Substation132 KV |  | 0.0 | 79.2 | 79.2 | 2033-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0l8e000000TPKNAA4 | PRO-003258 | 1
MODIFIED | Gate Status: '' -> '1' | Inveroykel Wind Farm | RWE RENEWABLES UK SWINDON LIMITED | Inveroykel Wind Farm 132kV |  | 0.0 | 191.4 | 191.4 | 2031-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0l8e0000010wmDAAQ | PRO-002831 | 1
MODIFIED | Gate Status: '' -> '1' | Jubilee Farm | Starlight Energy SPV 2 | Jubilee Farm 275kV Substation |  | 0.0 | 200.0 | 200.0 | 2034-08-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L000002yQX9QAM | PRO-002545 | 1
MODIFIED | Gate Status: '' -> '1' | Kellas Wind Farm | E Power Limited | Kellas Wind Farm 132kV Substation |  | 0.0 | 90.0 | 90.0 | 2030-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0l4L0000005iuZQAQ | PRO-002271 | 1
MODIFIED | Gate Status: '' -> '1' | Lightsource Lower Frankton | Lightsource Renewable UK Development Limited | Cheshire Connection Node A 400kV Substation |  | 0.0 | 240.0 | 240.0 | 2037-10-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000f4e1AAA | PRO-003859 | 1
MODIFIED | Gate Status: '' -> '1' | Lorg Extension Wind Farm | RWE Renewables UK Onshore Wind Limited | Lorg Extension Wind Farm 132/33kV Substation |  | 0.0 | 33.0 | 33.0 | 2029-08-13 | Scoping | Direct Connection | SPT | Wind Onshore | a0l4L0000005iynQAA | PRO-002430 | 1
MODIFIED | Gate Status: '' -> '1' | Nant Helen | SOLAR SECURITIES LIMITED | South Wales West Connection Node A 400kV Substation |  | 0.0 | 500.0 | 500.0 | 2037-10-31 | Scoping | Direct Connection | NGET | Demand;Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000010wgFAAQ | PRO-002766 | 1
MODIFIED | Gate Status: '' -> '1' | Navenby Farm | CODDINGTON 10 RENEWABLES LTD | Coddington 400kV Substation |  | 0.0 | 1000.0 | 1000.0 | 2034-10-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000001HnxlAAC | PRO-004045 | 1
MODIFIED | Gate Status: '' -> '1' | Patford Bridge Farm | 548 UK INVESTMENT HOLDINGS LIMITED | Patford Bridge 400kV Substation |  | 0.0 | 200.0 | 200.0 | 2033-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000010wYiAAI | PRO-002680 | 1
MODIFIED | Gate Status: '' -> '1' | Pivot Power Harker Hybrid | PIVOTED POWER LLP | Harker 400/132KV Substation |  | 0.0 | 57.0 | 57.0 | 2029-10-31 | Consents Approved | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005iu0QAA | PRO-001065 | 1
MODIFIED | Gate Status: '' -> '1' | Ranby | SSE DE SOLAR HOLDCO LIMITED | Jubilee Farm 275kV Substation |  | 0.0 | 600.0 | 600.0 | 2034-08-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L000002yQa8QAE | PRO-002557 | 1
MODIFIED | Gate Status: '' -> '1' | Ruith Cnoc | Ruith Cnoc Wind Farm Limited | New Dalchork 132kV Substation |  | 0.0 | 158.4 | 158.4 | 2037-10-31 | Scoping | Direct Connection | SHET | Wind Onshore | a0lJ9000000POuiIAG | PRO-006147 | 1
MODIFIED | Gate Status: '' -> '1' | SANDFORD | SSE DE SOLAR HOLDCO LIMITED | SANDFORD B 400kV SUBSTATION |  | 0.0 | 600.0 | 600.0 | 2037-10-20 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000010wRXAAY | PRO-002600 | 1
MODIFIED | Gate Status: '' -> '1' | SAVE OUR PLANET | SAVE OUR PLANET ENERGY LIMITED | Sussex and Romney Connection Node B 400kV Substation |  | 0.0 | 500.0 | 500.0 | 2037-10-31 | Scoping | Direct Connection | NGET | Demand;Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012iy3AAA | PRO-004613 | 1
MODIFIED | Gate Status: '' -> '1' | South Kyle 2 Wind farm | VATTENFALL WIND POWER LTD | South Kyle 2 132/33kV Substation |  | 0.0 | 92.4 | 92.4 | 2030-07-31 | Scoping | Direct Connection | SPT | Energy Storage System;Wind Onshore | a0l4L0000005ivbQAA | PRO-001963 | 1
MODIFIED | Gate Status: '' -> '1' | SSE Spittal Energy Park | SSE DE SOLAR HOLDCO LIMITED | Spittal 400kV |  | 0.0 | 600.0 | 600.0 | 2033-10-31 | Scoping | Direct Connection | SHET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000000TPKSAA4 | PRO-003259 | 1
MODIFIED | Gate Status: '' -> '1' | St Fergus | IB VOGT UK LTD | St Fergus |  | 0.0 | 100.0 | 100.0 | 2033-10-31 | Scoping | Direct Connection | SHET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012hvYAAQ | PRO-004557 | 1
MODIFIED | Gate Status: '' -> '1' | The Beacon | Beacon Solar Limited | West Country Connection Node C 400kV Substation |  | 0.0 | 1200.0 | 1200.0 | 2037-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0lJ9000000PDtEIAW | PRO-005046 | 1
MODIFIED | Gate Status: '' -> '1' | Upper Beoch Windfarm | BROCKWELL ENERGY LIMITED | New Cumnock North 132kV Substation |  | 0.0 | 80.0 | 80.0 | 2033-10-31 | Scoping | Direct Connection | SPT | Wind Onshore | a0l8e000001HoGMAA0 | PRO-004068 | 1
MODIFIED | Gate Status: '' -> '1' | Walham PV & BESS Sub | GLOUCESTER ENERGY PARK LIMITED | Walham 400kV Substation |  | 0.0 | 249.0 | 249.0 | 2033-11-17 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005j8WQAQ | PRO-002522 | 1
MODIFIED | Gate Status: '' -> '1' | West Melton PV & BESS Station | IBV WEST MELTON SOLAR PARK LIMITED | Leeds North Connection Node C 400kV Substation |  | 0.0 | 200.0 | 200.0 | 2033-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000001HoBfAAK | PRO-004061 | 1
MODIFIED | Gate Status: '' -> '1' | Willington PV & BESS | WILLINGTON ENERGY PARK LIMITED | Willington East 400kV Substation |  | 0.0 | 249.9 | 249.9 | 2033-10-31 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e000001HperAAC | PRO-004142 | 1