## Pot 3
Change Type | Count
New Entries | 0
Deleted Entries | 0
Modified Entries | 0
Detailed Change Records:

## Pot 1
Change Type | Count
New Entries | 0
Deleted Entries | 1
Modified Entries | 11
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
DELETED | Entry removed from TEC register. | Ratcliffe-on-Soar | ENSO GREEN HOLDINGS C LIMITED | Ratcliffe-On-Soar 132kV Substation |  | 0.0 | 190.0 | 190.0 | 2029-07-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005iyvQAA | PRO-001361 | 1
MODIFIED | Connection Date: '2025-11-30' -> '2027-10-31'; Gate Status: '' -> '2' | Berryburn Extension Wind Farm | BB2 WIND FARM LIMITED | Berryburn 275/33kV GSP Substation |  | 0.0 | 43.2 | 43.2 | 2027-10-31 | Consents Approved | Embedded | SHET | Wind Onshore | a0l4L0000005iUGQAY | PRO-001558 | 2
MODIFIED | Connection Date: '2026-08-16' -> '2027-10-30' | Bramley (tertiary) | BRAMLEY SOLAR LIMITED | Bramley 400kV Substation |  | 0.0 | 57.0 | 57.0 | 2027-10-30 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005ilOQAQ | PRO-000396 | 2
MODIFIED | Gate Status: '' -> '1' | Garlogie B-1 | GARLOGIE ENERGY CENTRE LIMITED | Garlogie Production B 275/33kV GSP |  | 0.0 | 50.0 | 50.0 | 2033-10-31 | Scoping | Embedded | SHET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012jIGAAY | PRO-004640 | 1
MODIFIED | Gate Status: '' -> '1' | Garlogie B-2 | GARLOGIE ENERGY CENTRE LIMITED | Garlogie Production B 275/33kV GSP |  | 0.0 | 50.0 | 50.0 | 2033-10-31 | Scoping | Embedded | SHET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012jILAAY | PRO-004641 | 1
MODIFIED | Gate Status: '' -> '1' | Garlogie C-1 | GARLOGIE ENERGY CENTRE LIMITED | Garlogie Production C 275/33kV GSP |  | 0.0 | 50.0 | 50.0 | 2033-10-31 | Scoping | Embedded | SHET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012jIQAAY | PRO-004642 | 1
MODIFIED | Gate Status: '' -> '1' | Garlogie PV and BESS A-1 | GARLOGIE ENERGY CENTRE LIMITED | Garlogie Production A 275/33kV GSP |  | 0.0 | 50.0 | 50.0 | 2033-10-31 | Scoping | Embedded | SHET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012jDoAAI | PRO-004636 | 1
MODIFIED | Gate Status: '' -> '1' | Garlogie PV and BESS A-2 | GARLOGIE ENERGY CENTRE LIMITED | Garlogie Production A 275/33kV GSP |  | 0.0 | 50.0 | 50.0 | 2033-10-31 | Scoping | Embedded | SHET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000012jDtAAI | PRO-004637 | 1
MODIFIED | Connection Date: '2025-05-31' -> '2027-05-30' | Indian Queens Energy Centre | IQ ENERGY CENTRE LIMITED | Indian Queens 400kV Substation |  | 0.0 | 47.5 | 47.5 | 2027-05-30 | Consents Approved | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005iZCQAY | PRO-001371
MODIFIED | Connection Date: '2030-08-30' -> '2028-04-28' | Mannington | BAYWA R.E. UK LIMITED | Mannington 400kV Substation |  | 0.0 | 47.5 | 47.5 | 2028-04-28 | Scoping | Direct Connection | NGET | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l4L0000005ibaQAA | PRO-001092
MODIFIED | Connection Date: '2027-08-27' -> '2030-06-14' | St Marys Isle Solar Farm | GRUPOTEC SOLAR UK 5 LIMITED | Tongland 132/33kV Substation |  | 0.0 | 36.0 | 36.0 | 2030-06-14 | Scoping | Embedded | SPT | Energy Storage System;PV Array (Photo Voltaic/solar) | a0l8e0000010wiLAAQ | PRO-002789
MODIFIED | Gate Status: '' -> '1' | Teviot Wind Farm | TEVIOT WF LIMITED | Teviot 400/132kV Substation |  | 0.0 | 522.9 | 522.9 | 2033-05-30 | Scoping | Direct Connection | SPT | Wind Onshore | a0l4L0000005iPbQAI | PRO-000855 | 1