## Pot 3
Change Type | Count
New Entries | 0
Deleted Entries | 0
Modified Entries | 0
Detailed Change Records:

## Pot 1
Change Type | Count
New Entries | 1
Deleted Entries | 1
Modified Entries | 24
Detailed Change Records:
Change Type | Change Details | Project Name | Customer Name | Connection Site | Stage | MW Connected | MW Increase / Decrease | Cumulative Total Capacity (MW) | MW Effective From | Project Status | Agreement Type | HOST TO | Plant Type | Project ID | Project Number | Gate
NEW | New entry in TEC register. | Chirmorie Wind Farm | CHIRMORIE WIND FARM LIMITED | Chirmorie Wind Farm substation | 1.0 | 0.0 | 91.0 | 91.0 | 2027-04-30 | Consents Approved | Direct Connection | SPT | Wind Onshore | a0l4L0000005inCQAQ | PRO-000094-1 | 2
DELETED | Entry removed from TEC register. | Chirmorie Wind Farm | CHIRMORIE WIND FARM LIMITED | Chirmorie 132/33kV Substation |  | 0.0 | 91.0 | 91.0 | 2026-10-09 | Consents Approved | Direct Connection | SPT | Wind Onshore | a0l4L0000005inCQAQ | PRO-000094
MODIFIED | Gate Status: '' -> '1' | Cairnborrow Wind Energy Hub | BPUWL 29 LIMITED | Cairnford GSP |  | 0.0 | 43.2 | 43.2 | 2031-10-31 | Scoping | Embedded | SHET | Energy Storage System;Wind Onshore | a0l8e0000012eoKAAQ | PRO-004377 | 1
MODIFIED | Gate Status: '' -> '1' | Causeymire 2 Wind Farm | HEADWIND DEVELOPMENT SERVICES LIMITED | Mybster 4 132/33kV GSP Substation |  | 0.0 | 39.6 | 39.6 | 2034-10-31 | Scoping | Embedded | SHET | Wind Onshore | a0l8e0000012kqcAAA | PRO-004778 | 1
MODIFIED | Gate Status: '' -> '1' | Cogle Moss Wind Farm | COGLE MOSS RENEWABLES LLP | Mybster 2 132/33kV Substation |  | 0.0 | 36.0 | 36.0 | 2025-08-31 | Consents Approved | Embedded | SHET | Wind Onshore | a0l4L0000005iWrQAI | PRO-000973 | 1
MODIFIED | Gate Status: '' -> '1' | Crakaig Wind Energy Hub | CRAKAIG WIND ENERGY HUB LIMITED | BRORA 132/33KV GRID SUPPLY POINT SUBSTATION |  | 0.0 | 60.0 | 60.0 | 2034-10-31 | Scoping | Embedded | SHET | Energy Storage System;Wind Onshore | a0l8e000000exYDAAY | PRO-003734 | 1
MODIFIED | Gate Status: '' -> '2' | Crystal Rig IV Wind Farm | CRYSTAL RIG IV LIMITED | Crystal Rig 400kV substation |  | 0.0 | 48.2 | 48.2 | 2025-10-13 | Built | Direct Connection | SPT | Wind Onshore | a0l4L0000005ipMQAQ | PRO-000520 | 2
MODIFIED | Connection Date: '2025-07-31' -> '2025-12-08'; Gate Status: '' -> '2' | Cumberhead West Wind Farm | CUMBERHEAD WEST WIND FARM LTD. | Cumberhead 33kV |  | 0.0 | 114.0 | 114.0 | 2025-12-08 | Built | Direct Connection | SPT | Wind Onshore | a0l4L0000005ix7QAA | PRO-000423 | 2
MODIFIED | Gate Status: '' -> '1' | Daviot Windfarm BEGA | CUBICO UK DEVELOPMENT LIMITED | INVERNESS 132/33KV GRID SUPPLY POINT SUBSTATION |  | 0.0 | 45.0 | 45.0 | 2030-10-31 | Scoping | Embedded | SHET | Energy Storage System;Wind Onshore | a0lJ9000000blQPIAY | PRO-004874 | 1
MODIFIED | Connection Date: '2025-06-30' -> '2025-10-05'; Gate Status: '' -> '2' | Douglas West Extension | DOUGLAS WEST EXTENSION LTD | Douglas West Extension Windfarm |  | 0.0 | 60.0 | 60.0 | 2025-10-05 | Built | Direct Connection | SPT | Wind Onshore | a0l4L0000005ixIQAQ | PRO-000422 | 2
MODIFIED | Connection Date: '2025-05-30' -> '2026-04-16'; Gate Status: '' -> '2' | Enoch Hill | RWE Renewables UK Onshore Wind Limited | Enoch Hill 132/33kV Substation |  | 0.0 | 69.0 | 69.0 | 2026-04-16 | Built | Direct Connection | SPT | Energy Storage System;Wind Onshore | a0l4L0000005iomQAA | PRO-000152 | 2
MODIFIED | Connection Date: '2027-10-31' -> '2028-06-30'; Gate Status: '' -> '2' | Greenburn Mixed Technology | REG GREENBURN LIMITED | Greenburn Mixed Technology 132kV Substation |  | 0.0 | 90.0 | 90.0 | 2028-06-30 | Scoping | Direct Connection | SPT | Wind Onshore | a0l4L0000005ibVQAQ | PRO-001006 | 2
MODIFIED | Gate Status: '' -> '1' | High Brenfield 1 | High Brenfield Wind Farm Limited | Craig Murrail 275/33kV GSP Substation |  | 0.0 | 52.8 | 52.8 | 2034-10-31 | Scoping | Embedded | SHET | Wind Onshore | a0lJ9000000blQUIAY | PRO-004875 | 1
MODIFIED | Gate Status: '' -> '1' | High Brenfield 2 | High Brenfield Wind Farm Limited | Craig Murrail GSP |  | 0.0 | 20.4 | 20.4 | 2034-10-31 | Scoping | Embedded | SHET | Wind Onshore | a0lJ9000000blQZIAY | PRO-004876 | 1
MODIFIED | Gate Status: '' -> '2' | Hopsrig Wind Farm | HOPSRIG WIND FARM LIMITED | Hopsrig Collector Substation |  | 0.0 | 48.0 | 48.0 | 2027-10-31 | Consents Approved | Direct Connection | SPT | Wind Onshore | a0l4L0000005isfQAA | PRO-000318 | 2
MODIFIED | Gate Status: '' -> '2' | Kilgallioch Wind Farm | SCOTTISHPOWER RENEWABLES (UK) LIMITED | Kilgallioch 275kV Substation | 2.0 | 0.0 | 46.0 | 274.0 | 2025-04-08 | Built | Direct Connection | SPT | Wind Onshore | a0l4L0000005imcQAA | PRO-000065-2 | 2
MODIFIED | Gate Status: '' -> '1' | Killean Wind Farm | Renewable Energy Systems Limited | CARRADALE 3 132/33KV GRID SUPPLY POINT SUBSTATION |  | 0.0 | 60.0 | 60.0 | 2034-10-31 | Scoping | Embedded | SHET | Wind Onshore | a0lJ9000000POB6IAO | PRO-006009 | 1
MODIFIED | Connection Date: '2026-10-31' -> '2027-07-16'; Gate Status: '' -> '2' | Lairg II Wind Farm | LAIRG II LLP | Lairg II 132kV Substation |  | 0.0 | 50.0 | 50.0 | 2027-07-16 | Consents Approved | Direct Connection | SHET | Wind Onshore | a0l4L0000005ibkQAA | PRO-001434 | 2
MODIFIED | Connection Date: '2027-06-30' -> '2029-10-30'; Gate Status: '' -> '2' | Lethans Wind Farm | Lethans Wind Farm Limited | Lethans Collector Substation |  | 0.0 | 132.0 | 132.0 | 2029-10-30 | Consents Approved | Direct Connection | SPT | Wind Onshore | a0l4L0000005iZ9QAI | PRO-001367 | 2
MODIFIED | Connection Date: '2027-10-30' -> '2029-10-30'; Gate Status: '' -> '2' | Lethans Wind Farm Extension | LETHANS EAST WIND FARM LIMITED | Lethans Collector 132kV Substation |  | 0.0 | 85.0 | 85.0 | 2029-10-30 | Scoping | Direct Connection | SPT | Wind Onshore | a0l8e0000011ywSAAQ | PRO-003553 | 2
MODIFIED | Gate Status: '' -> '2' | Loganhead Windfarm | LOGANHEAD WF LIMITED | Hopsrig Collector Substation |  | 0.0 | 36.0 | 36.0 | 2027-10-31 | Awaiting Consents | Direct Connection | SPT | Wind Onshore | a0l4L0000005isNQAQ | PRO-000306 | 2
MODIFIED | Gate Status: '' -> '1' | Millennium East | Renantis UK Limited | FORT AUGUSTUS 2 400/33kV GRID SUPPLY POINT SUBSTATION |  | 0.0 | 49.9 | 49.9 | 2035-10-31 | Scoping | Embedded | SHET | Wind Onshore | a0l8e000000f7gMAAQ | PRO-004010 | 1
MODIFIED | Connection Date: '' -> '2026-02-04'; Gate Status: '' -> '2' | North Kyle New Cumnock | NORTH KYLE WIND FARM LIMITED | New Cumnock 275/132kV Substation |  | 212.0 | 0.0 | 212.0 | 2026-02-04 | Built | Direct Connection | SPT | Wind Onshore | a0l4L0000005inuQAA | PRO-000474 | 2
MODIFIED | Gate Status: '' -> '1' | Novar 2 Wind Farm | HEADWIND DEVELOPMENT SERVICES LIMITED | Alness GSP |  | 0.0 | 43.2 | 43.2 | 2032-10-31 | Scoping | Embedded | SHET | Wind Onshore | a0l8e0000012kptAAA | PRO-004775 | 1
MODIFIED | Gate Status: '' -> '1' | Stoneygroves PV | Enviromena Project Management UK Limited | Charleston GSP 132/33kV |  | 0.0 | 20.0 | 20.0 | 2031-10-30 | Scoping | Embedded | SHET | PV Array (Photo Voltaic/solar) | a0lJ9000000POkcIAG | PRO-006127 | 1
MODIFIED | Gate Status: '' -> '1' | Windburn | WINDBURN WIND FARM LIMITED | Braco West GSP |  | 0.0 | 75.0 | 75.0 | 2035-10-31 | Scoping | Embedded | SHET | Energy Storage System;Wind Onshore | a0l8e0000012kkqAAA | PRO-004768 | 1